## List Of Requirements
A. Contract and product model
1 | Is Murabaha a separate financing type/entity in your fork, or a Fineract loan product with additional fields? Show the data model (tables added or altered).
FOO | Loan Product gets an Islamic Product flag + Financing Type dropdown; the financing account is the existing loan account with added fields
2 | Which Murabaha variants are supported: commodity Murabaha (Tawarruq via metals/commodity broker), goods Murabaha (vehicle, equipment, purchase order), Murabaha to the purchase orderer? How do they differ in configuration?
FOO | Currently supported through a generic Murabaha model covering the common financing components. The model is designed to be scalable and can be extended to support specific variants such as Goods Murabaha, Commodity Murabaha/Tawarruq, and Murabaha to the Purchase Orderer based on business requirements.
3 | Where are cost price, profit amount, profit rate, selling price and tenor stored, and which is the master value? If a user enters a profit rate, is the profit amount derived once at sale execution and then frozen?
FOO | Cost Price is captured from the selected commodity and used as the Financing Amount. Profit is calculated by the LMS based on the configured Nominal Profit Rate and Profit Method, while Selling Price is derived from Cost Price + Profit. Product-level calculation rules can be centrally controlled to prevent account-level overrides where required.
4 | Can the profit rate be expressed as a flat rate on cost, an effective/annualised rate for disclosure, or both? How is the APR-equivalent calculated for CBB consumer-protection disclosures?
FOO | The Murabaha pricing model supports configurable profit calculation through the LMS, including Nominal Profit Rate, Profit Method and Profit Calculation Period. The model can support different pricing methodologies based on product configuration. Effective/annualised rate and CBB-specific APR-equivalent disclosure are not currently part of the Murabaha configuration and can be added based on the applicable CBB calculation and disclosure requirements.
5 | Is the selling price contractually immutable after execution? Show what happens if a user tries to edit the profit or rate on an active account - is it blocked, or does it silently recalculate?
FOO | Murabaha pricing and calculation rules are controlled at product level and can be restricted from account-level override. Once the financing is approved, Islamic financing and commodity information becomes read-only, supporting preservation of the agreed financing terms.
6 | How is the transaction sequence enforced: promise to purchase -> bank purchase of asset -> bank ownership -> sale to customer (offer/acceptance) -> deferred payment? Are these distinct states with timestamps and maker-checker, or one single 'disburse' action?
FOO | Yes. The LMS supports a dedicated Murabaha contractual lifecycle alongside the existing financing lifecycle. The controlled lifecycle includes Promise to Purchase → Purchase Instructed → Asset Purchased → Ownership Confirmed → Possession Confirmed → Offer Created → Customer Accepted → Murabaha Sale Executed → Receivable Active. The Murabaha lifecycle is maintained separately from the standard financing status, while the existing financing approval, disbursement and activation capabilities continue to be reused.
7 | Is there any point at which the customer's debt exists before the bank owns the asset? Show how the system prevents sale execution without a recorded purchase/ownership event.
FOO | Yes. The LMS enforces the required Murabaha sequence. Murabaha Sale Execution is not permitted until the asset has been purchased, ownership and possession have been confirmed, the required evidence has been provided, the Murabaha offer has been created and the customer has accepted the applicable offer. Financing approval alone does not create an active customer receivable, and disbursement/activation cannot occur before Murabaha Sale Execution.
8 | Can the customer act as the bank's agent (Wakala) to purchase the asset? How is the agency recorded and how is the purchase invoice evidenced?
FOO | The current Murabaha implementation supports capturing the underlying commodity/asset, supplier information and Cost Price. A dedicated Wakala (agency) workflow is not currently modeled as a separate component; however, the solution is extensible to support customer-as-agent scenarios, including recording the agency appointment/agreement, purchase details, supplier invoice and supporting documentation, with the required audit trail and maker-checker controls.
9 | How are commodity/asset details evidenced - description, supplier, purchase invoice reference, purchase date, delivery/possession confirmation (constructive or physical)? Which are mandatory before sale?
FOO | The LMS captures structured Murabaha purchase, ownership and possession information, including asset/commodity details, supplier, purchase price and currency, supplier invoice/reference, purchase date, asset/lot reference, ownership confirmation and evidence, and physical or constructive possession confirmation and evidence. Supporting documents are associated with the applicable Murabaha lifecycle stage. Evidence requirements can be configured as Mandatory or Optional by lifecycle stage, and the system blocks the applicable lifecycle transition when mandatory evidence is missing.
10 | For 'Commodity Transaction Integration': which external commodity platform(s) are integrated? Is the purchase and onward sale to a third party (in Tawarruq) recorded with prices and timestamps so a Shariah auditor can reconstruct the full chain?
FOO | The integration is designed to work with either an external commodity provider or FOO Commodity Management, with configurable endpoints and credentials, rather than being tied to one specific platform. The current scope covers commodity search, retrieval and validation, but does not manage the full commodity trading or ownership lifecycle within the LMS. The integration framework already exists; full Tawarruq transaction-chain recording, including purchase/onward-sale details and Sharia audit reconstruction, would be an extension.
11 | Is a floating/repricing profit rate deliberately blocked? How are binding vs non-binding promise to purchase (Wa'd) and Hamish Jiddiyyah (security deposit) handled if the customer backs out?
FOO | Murabaha products can be configured with a fixed nominal profit rate and without linkage to floating interest rates. The product configuration explicitly controls whether the rate is linked to a floating-rate mechanism; for Murabaha, this can be disabled to maintain fixed pricing. Wa'd and Hamish Jiddiyyah are not currently modeled as dedicated workflows and would be extensions where required.
B. Repayment schedule
12 | Show a generated schedule for a sample deal (cost 10,000, profit 1,500, 24 months). How is each instalment split between cost recovery and profit? Which allocation method - equal instalments with amortised profit, straight-line, or configurable?
FOO | Validated with a sample Murabaha deal of BHD 10,000 cost, BHD 1,500 Profit and a 24-month tenor. The Profit allocation method is configurable at Loan Product level. The LMS supports Flat and Declining Balance Profit methods, together with configurable amortization using Equal Installments or Equal Principal Payments. Yes. Please refer to the two scenarios attached under 'Schedule - req 12'
13 | Does the schedule total exactly equal the selling price? Prove the sum of profit across all instalments equals the contracted profit to the fil, with no rounding residue.
FOO | Yes. Please refer to the two scenarios attached under 'Schedule - req 12'
14 | Is the profit component of each instalment fixed at execution, or recomputed from 'outstanding balance x rate x days' each period?
FOO | Profit is calculated when the repayment schedule is generated and remains fixed according to the contractual schedule; it is not recomputed each period based on the actual outstanding balance × rate × days.
15 | If the sale date shifts, the first instalment date moves, or a holiday/business-day rule pushes a due date, does total profit change?
FOO | Validated from our side: the total contracted Profit remains unchanged when the sale date, first instalment date, or due date shifts due to holiday/business-day rules.
16 | Grace periods, moratorium, balloon/step-up structures - supported? Does profit accrue during grace in a way that increases total profit?
FOO | Grace periods and moratorium are supported. Validated from our side that the total contracted Profit remains unchanged after applying a Mid-term Grace Period.
17 | Partial disbursement, tranches and top-ups: blocked (a Murabaha is a single completed sale) or handled as a new contract? What does Fineract's multi-disbursement configuration do in your fork?
FOO | The LMS supports configurable multi-disbursement and top-up capabilities at product level. For Murabaha products, these capabilities can be disabled where the financing structure requires a single completed sale. Additional financing can be structured through a separate Murabaha financing.
C. Early settlement and rebate (Ibra')
18 | On early settlement, how is the outstanding amount computed? The full remaining selling price is contractually due; any reduction is a discretionary rebate (Ibra'). Does the system post an explicit rebate transaction, or auto-waive 'unaccrued interest'?
FOO | The LMS supports a dedicated Early Settlement with Ibra’ process. The system determines the outstanding contractual amount and calculates the applicable Ibra’ separately according to the configured Ibra’ method. The settlement preview clearly presents the contractual outstanding amount, applicable Ibra’ and resulting settlement amount. Ibra’ is therefore handled explicitly as a rebate against the contractual Murabaha amount rather than being treated as an automatic waiver of “unaccrued interest.
19 | Is the Ibra' formula configurable (e.g. unearned profit less admin fee, or fixed percentage) and approval-controlled through maker-checker?
FOO | Yes. Ibra’ calculation is configurable at Murabaha product level. Supported calculation methods include Manual amount, Percentage, eligible Unearned Profit and Unearned Profit less applicable Administration / Early Settlement Charges, with the applicable charge configuration referenced from the Murabaha product. The Early Settlement with Ibra’ process supports calculation preview and approval/rejection through the existing maker-checker framework where enabled.
20 | For partial prepayments, does the system re-amortise (interest logic) or reduce remaining instalments while total profit stays fixed unless a rebate is explicitly granted?
FOO | Supported through configuration. Recalculate Profit = No → Murabaha contractual Profit remains fixed and is not automatically reduced through conventional interest recalculation. Where Profit Recalculation is disabled, a partial prepayment does not recalculate the contractual Murabaha Profit. Any reduction of contractual Profit must be explicitly processed as Ibra’ in accordance with the configured Ibra’ rules and applicable approval controls.
21 | How is the rebate presented on settlement letters and statements - as a reduction of the contractual selling price, not as 'interest saved'?
FOO | Yes. Ibra’ calculation is configurable at Murabaha product level. Supported calculation methods include eligible Unearned Profit and Unearned Profit less applicable Administration / Early Settlement Charges, with the applicable charge configuration referenced from the Murabaha product. The Early Settlement with Ibra’ process supports calculation preview and approval/rejection through the existing maker-checker framework where enabled.
D. Late payment, default and restructuring
22 | Confirm no additional profit, interest or compounding accrues after a due date. Show penalty configuration and prove Fineract's interest-recalculation and penalty-on-overdue-interest paths are disabled or removed for Murabaha.
FOO | Murabaha products can be configured with Profit Recalculation disabled, floating-rate linkage disabled and no compounding, ensuring that the contractual Profit is not automatically increased due to late payment. The existing LMS provides these controls at product level.
23 | Late payment charges: fixed or percentage, and are they routed to a charity account rather than income per AAOIFI? Show the GL mapping and the report giving the charity payable balance.
FOO | The LMS already supports configurable late-payment charges, including flat and percentage-based charges, together with penalty receivable and accounting mappings. For Murabaha, an enhancement will allow the applicable late-payment amounts to be routed to a dedicated Charity Payable liability account rather than Income from Penalties, ensuring that such amounts are segregated from the institution's income. Charity balances can then be exposed through the applicable accounting/reporting layer.
24 | Can late charges be waived, is the waiver audited, and is charity payout tracked?
FOO | Late-charge waiver is already supported by the LMS and is recorded as a distinct transaction, providing traceability of waived amounts. Charity amounts collected under the treatment described above can be maintained separately through Charity Payable. Where required by BEDE's operating model, the solution can be extended to track subsequent charity distributions, including beneficiary, amount, payment date/reference, supporting evidence, approval and reconciliation against the Charity Payable balance. Alternatively, the actual charity payout can be handled through the accounting/ERP layer while LMS maintains the relevant balance and transaction information.
25 | Restructuring/rescheduling: since the debt cannot be increased, how is tenor extension handled? Show that outstanding debt is redistributed without added profit, and that refinancing is a genuinely new sale with a new asset, not a rollover of existing debt.
FOO | The LMS already provides a rescheduling framework with approval/rejection workflow, and Profit recalculation can be disabled at product level. For Murabaha, rescheduling can be controlled so that Profit/rate recalculation is not applied and the existing contractual outstanding amount is redistributed over the revised schedule without increasing the Murabaha debt. Any approved reduction in Profit can be handled separately through Ibra'. Where refinancing is required, it would be treated as a new Murabaha financing/sale rather than an increase or rollover of the existing Murabaha debt.
26 | Write-off, provisioning (IFRS 9 stages / CBB requirements), and treatment of outstanding unearned profit on write-off.
FOO | The LMS already supports loan write-off, accounting entries and configurable provisioning based on days overdue, provisioning percentages and GL mappings. Where BEDE requires full IFRS 9/CBB ECL and staging, the existing framework can be extended or integrated with the applicable impairment methodology. Murabaha-specific accounting treatment can also be extended, based on the approved accounting model, to distinguish financing Cost, recognized Profit and deferred/unearned Profit, including their treatment during write-off and subsequent recoveries.
E. Accounting and GL
27 | Provide the full chart-of-account mapping and journal entries at each event: asset purchase, asset held before sale, sale to customer, instalment collection, periodic profit recognition, early settlement with rebate, late charge to charity, write-off.
FOO | The LMS provides an established GL and journal-entry framework covering financing disbursement, accrual, repayment, waiver and write-off. For Murabaha, this framework can be extended with a dedicated posting matrix covering asset purchase and holding, Murabaha sale, instalment collection, Profit recognition, Ibra', late-payment/Charity treatment and write-off, based on BEDE's approved accounting and Shariah treatment.
28 | On sale execution, is the receivable recorded at gross selling price with a contra deferred/unearned Murabaha profit account (AAOIFI FAS 28), or at cost only with profit recognised as billed? Configurable?
FOO | The Murabaha financing model already maintains Cost Price, Profit and Selling Price. The current accounting framework records the financing amount through the existing Loan Portfolio and accrual model. Where BEDE requires the receivable to be accounted for at gross Selling Price with Deferred/Unearned Murabaha Profit separately recognised, this accounting treatment can be added using dedicated GL mappings and the recognition method approved by BEDE Finance, Shariah and the applicable accounting requirements.
29 | How is profit recognised - proportionately over the contract period, or only when instalments are paid? Show the accrual job and entries, and confirm it is time-based on fixed profit, not 'outstanding principal x rate'.
FOO | Profit accrual and accounting entries are supported by the LMS and can be processed through EOD/accrual jobs. For Murabaha, we will validate and demonstrate that the fixed contractual profit is recognised over the financing period according to the agreed schedule, rather than being dynamically recalculated based on outstanding principal × rate.
30 | Which Fineract GL account roles were reused (loanPortfolioAccount, interestOnLoanAccount, incomeFromFeeAccount, overpaymentLiability)? Were new roles added (Murabaha inventory/asset, deferred profit, charity payable), or were interest accounts merely renamed?
FOO | Existing Fineract accounting roles are leveraged for the current Murabaha implementation.
31 | How is the asset shown on the balance sheet between purchase and sale? Is there an inventory/asset GL entry at all?
FOO | The current Murabaha implementation captures the Commodity, Supplier and Cost Price, but the asset is not currently represented as a separate accounting balance between purchase and sale. Where required by BEDE's accounting model, an Asset Purchase/Ownership accounting event can be introduced to recognise the asset through a Murabaha Inventory/Asset account when purchased and clear it when the Murabaha sale is executed.
32 | Suspended profit: when an account becomes non-performing, is profit recognition suspended and reversed to a suspense account? Show the days-past-due trigger and entries.
FOO | The LMS already supports DPD-based overdue/NPA identification and provides the underlying accounting and suspense-account framework. A Murabaha-specific Profit Suspension policy can be introduced to stop or adjust Profit recognition when the applicable DPD threshold is reached and apply the required suspense, recovery or write-off treatment according to BEDE's approved accounting policy.
33 | Multi-currency Murabaha (e.g. cost in USD, financing in BHD): how is FX on the purchase leg accounted?
FOO | The LMS supports currencies at financing/account and journal-entry level. Where the asset purchase currency differs from the Murabaha financing currency, the Murabaha purchase flow can be extended to capture the supplier purchase currency and applicable exchange rate and generate the required inventory, supplier settlement and FX gain/loss accounting entries according to BEDE's approved multi-currency accounting policy.
34 | Odoo export: show Murabaha entries arriving in Odoo with correct account codes and deferred profit reconciled between Fineract and Odoo.
FOO | The existing Odoo integration already exports LMS journal entries with their GL account codes, currency and amounts and provides reconciliation controls for exported journals. Once the Murabaha-specific accounting entries and GL mappings are introduced, the same integration can be extended to export these entries and reconcile relevant Murabaha balances, including Inventory/Asset, Gross Murabaha Receivable, Deferred Profit, Ibra' and Charity Payable, between the LMS and Odoo.
F. Fees, charges and tax
35 | Which fees are permitted (processing, documentation, actual-cost-based) and how are they prevented from being disguised profit (e.g. percentage of finance amount)? Is fee income booked separately from profit?
FOO | The LMS supports configurable charges with multiple calculation methods, allowing Murabaha products to be configured with only the applicable Sharia-approved fees, such as processing, documentation and actual-cost-based charges. Fee income and financing Profit are maintained through separate accounting mappings.
36 | Takaful on the asset: captured as pass-through charge, capitalised into cost before profit, or separate?
FOO | Takaful/insurance can be configured using the existing Charge functionality, allowing it to be maintained separately from Murabaha Profit and configured using the applicable calculation and accounting treatment. In line with BEDE's current requirement, insurance can be configured as a percentage of the finance amount and amortised across the financing tenure. If required, an explicit Insurance/Takaful classification can be introduced to distinguish it from other fees in schedules, APIs, accounting and reporting.
37 | TAX enhancement: are taxes computed on fees only and never on profit or the Murabaha debt?
FOO | Yes. The TAX functionality applies Tax Groups at charge level, with tax calculated on the applicable fee/charge amount rather than directly on Murabaha Profit or the financing debt. For Murabaha products, Tax Groups can therefore be configured only for the approved taxable fees, while Profit and other non-taxable financing components remain outside the tax calculation.
G. Documents and disclosures
38 | Does the system generate contract documents - promise to purchase, purchase confirmation, offer/acceptance sale contract, repayment schedule - from account data? Which templating engine, and are templates configurable by us?
FOO | The LMS provides the underlying customer, financing, commodity and repayment-schedule data, together with document-management capabilities and reusable templating infrastructure. Dedicated Murabaha contractual documents such as Promise to Purchase, Purchase/Ownership Confirmation, Offer & Acceptance and Murabaha Sale Contract are not currently generated as part of the Murabaha workflow and can be introduced as an enhancement. Existing templating uses Thymeleaf, while business-managed/versioned contract templates would require an additional configuration capability if BEDE requires templates to be maintained without deployment.
39 | Is CBB Volume 5 / consumer-protection disclosure supported - total cost of financing, profit amount, selling price, APR-equivalent, early settlement terms?
FOO | The Murabaha solution already maintains the core financing information required for disclosure, including Cost Price, Profit, Selling Price, repayment schedule, fees and financing totals. The LMS also provides underlying rate and repayment information. A dedicated CBB-compliant disclosure layer, including the applicable APR-equivalent calculation, early-settlement/Ibra' disclosure and regulator-approved presentation, is not currently implemented and can be added based on the applicable CBB calculation and disclosure requirements.
40 | Do statements show cost/profit split, remaining selling price and any rebate, using Islamic terminology and never 'interest'? Check API field names too, since our in-house app will consume them.
FOO | The Murabaha implementation already introduces Cost Price, Profit and Selling Price and uses Islamic terminology at the customer-facing financing level while retaining the existing LMS calculation engine for backward compatibility. The underlying Fineract APIs still contain conventional field names such as interest, and Ibra' is not currently exposed as a dedicated Islamic transaction/field. The API and statement layer can therefore be enhanced to expose explicit Murabaha-native fields and terminology—including Cost, Profit, Selling Price, remaining Selling Price and Ibra'—so consuming applications do not need to interpret or relabel conventional fields.
H. Shariah governance and audit
41 | Has this implementation been reviewed by a Shariah board or advisory firm, or deployed at a licensed Islamic FI? Which standard was it built to - AAOIFI Shariah Standard 8, AAOIFI FAS 28, or a specific bank's product manual? Provide the certificate or reference.
FOO | The Murabaha module has been designed to support Islamic financing requirements through dedicated Islamic Product and Murabaha configuration, including Commodity, Cost Price, Profit and Selling Price. Formal certification or approval by a Shariah Board/advisory firm is not currently part of the available implementation references. The solution can be reviewed against BEDE's approved product manual and applicable AAOIFI/CBB requirements, with any resulting controls incorporated into the implementation.
42 | Can a Shariah auditor reconstruct, from the audit trail alone, the full sequence of ownership transfer, prices and timestamps for any account?
FOO | The LMS provides comprehensive audit and maker-checker capabilities, including traceability of system operations, actors and financing events. Murabaha-specific information such as Commodity, Supplier, Cost Price, Profit and Selling Price is also maintained. The audit model can be extended with explicit ownership, possession, offer, acceptance and sale-execution events and their supporting evidence, allowing a Shariah auditor to reconstruct the complete Murabaha transaction sequence.
43 | Which upstream Fineract behaviours were disabled or overridden to make Murabaha compliant, and how do you ensure future upstream upgrades don't re-enable them (regression tests)?
FOO | Murabaha products already support configuration of key financing controls, including disabling Profit Recalculation, floating-rate linkage and compounding. Additional Murabaha-specific validations can enforce the approved Shariah configuration and prevent prohibited conventional options from being enabled. These controls can be covered by automated regression tests as part of the Fineract upgrade process to ensure they remain enforced following upstream upgrades.
44 | Can Murabaha and conventional loan products coexist in the same tenant, or is it a fork-wide switch? Can conventional products be disabled entirely for a fully Islamic company?
FOO | Yes. Islamic financing is configured at Loan Product level through the Islamic Product and Financing Type settings, allowing Murabaha and conventional products to coexist within the same tenant while preserving the existing conventional product behaviour. For institutions operating on a fully Islamic basis, an additional tenant-level Islamic Only control can be introduced, if required, to restrict the creation and use of conventional products.
I. Live scenario tests (schedule a meeting to run the following three scenarios on your instance)
45 | Scenario 1: 24-month deal paid exactly on time. Confirm schedule sum equals selling price and show the GL at month 12.
FOO | Validated. Refer to Sheet 'Scenario 1' A 24-month Murabaha financing was tested with a Cost Price of BHD 10,000 and contracted Profit of BHD 1,500, resulting in a Selling Price of BHD 11,500. The generated repayment schedule reconciles exactly to the Selling Price, with no residual balance at maturity. At month 12, the GL entry for the installment correctly separates cost recovery and Profit: BHD 416.67 applied to the financing amount and BHD 62.50 to Profit, against a total payment of BHD 479.17. The financing was subsequently completed through month 24, reaching a zero financing balance. The total Profit accrual was BHD 1,500.00, with the corresponding GL entry posted as Dr Profit Receivable / Cr Profit Received from Borrowers for BHD 1,500.00.
46 | Scenario 2: same deal settled early at month 10. Show the rebate computation and journal entries.
FOO | Validated. Early settlement with Profit rebate was tested using the existing LMS waiver and prepayment capabilities. The remaining contracted Profit can be waived before early settlement, and the settlement amount is adjusted accordingly. In the tested scenario, the outstanding amount before rebate was BHD 7,666.64, comprising BHD 6,666.64 financing amount and BHD 1,000.00 remaining Profit. Following a BHD 1,000.00 Profit rebate, the remaining Profit was reduced to BHD 0.00 and the early settlement amount was reduced to BHD 6,666.64. The existing capability can be extended with dedicated Ibra’ terminology, configurable rebate calculation and approval controls.
47 | Scenario 3: same deal 90 days late on instalment 5. Show that the debt did not grow, where the late charge went, and what the accrual job did.
Validated. Refer to Sheet 'Scenario 3'

## Scenario 1
Scenario 1
Installments 1–12 have been paid, and installments 13 onward remain outstanding.
Loan Account - General Details - after 12 installments

## Scenario 2
Scenario 2
Initial Status
Reaching Month 10 (After 9 Installments)
Prepay Screen without Ibra' | Prepay Screen After Ibra'

## Scenario 3
Scenario 3
already at 90 Past Due Days
Accrual Accounting entries
Accrual

## Schedule - req12
Scenario 1 : Declining Balance + Equal Installments:
Scenario 2 :Flat + Equal Installments:
Example after Mid TErm Grace ==> Profit remain the same

## gaps Assessment
BEDE | What BEDE wants | What we already have | Gap | Required Enhancement
C. Early settlement and rebate (Ibra')
18 | Early settlement = remaining contractual amount, with any reduction handled as explicit Ibra' | ✅ Prepay Loan calculates remaining Principal/Financing Amount + Interest/Profit + Fees. ✅ Interest Payment Waiver allows a partial or full manual waiver and reduces the Prepay amount. | 🟡 Partial — waiver exists but is generic Interest Payment Waiver, not Ibra'. We also found the waiver transaction allocation/journal issue that needs fixing. | For Islamic/Murabaha products, expose the existing waiver as Ibra' / Rebate in the early-settlement process and record the rebate amount correctly.
19 | Configurable Ibra' formula + maker-checker | ✅ Manual waiver amount already supported. | 🟡 Partial — no Ibra' calculation rule such as unearned Profit less fee / percentage. No dedicated Ibra' approval flow established. | Add Ibra' configuration at Murabaha product level and apply existing maker-checker to Ibra' requests.
20 | Partial prepayment should not automatically change contractual Profit unless Ibra' is granted | ✅ Partial repayments supported. ✅ Product has Recalculate Profit = Yes/No. | 🟢 Supported through configuration. | No new calculation functionality required. For Murabaha products, configure Recalculate Profit = No. As an additional control, we can enforce/default this setting for Murabaha products so Profit is not recalculated through the standard engine. Any explicit Profit reduction can be handled through Ibra'.
21 | Settlement documents show Selling Price and Ibra', not “interest saved” | ✅ Murabaha already has Cost Price, Profit and Selling Price. | 🟡 Partial — no dedicated Ibra' information in settlement output. | Add Ibra' amount and Islamic labels to settlement details/document.
D. Late payment, default and restructuring
22 | No additional Profit, interest or compounding after due date; conventional recalculation and penalty-on-Profit paths must not apply to Murabaha. | ✅ Product supports Recalculate Profit = Yes/No. ✅ Floating-rate linkage can be disabled. ✅ Existing engine provides configurable compounding/recalculation behavior. | 🟢 Supported through configuration | Add optional Sharia enforcement for Murabaha: default/enforce Recalculate Profit = No, no compounding and no floating-rate linkage. Restrict late-charge calculation methods based on Profit or Amount + Profit where required by the approved Sharia rules.
23 | Late-payment charges may be fixed/% according to approved Sharia rules and must not be recognized as bank income; applicable amounts should be routed to Charity Payable, with charity-balance reporting. | ✅ LMS supports configurable charges, including flat and percentage-based charges. ✅ Existing accounting supports Penalties Receivable and Income from Penalties GL mappings. ❌ The Income from penalties mapping only accepts Income-type GLs, so a Charity Payable Liability GL cannot currently be selected. | 🟡 Partial / Enhancement — charge calculation already exists, but the current accounting model routes penalties to Income. It cannot currently route Murabaha late-payment amounts directly to a Liability → Charity Payable account. | For Islamic/Murabaha products, introduce a Sharia late-payment treatment, e.g. Late Payment Treatment = Charity, with a dedicated Charity Payable Account mapped to a Liability GL (e.g. Other Liabilities → Charity Payable) instead of Income from penalties. Provide reporting for assessed, collected, waived and outstanding charity amounts.
24 | Late charges can be waived with auditability, and subsequent charity payouts can be tracked and reconciled. | ✅ Charge waiver already exists. ✅ Waiver creates a distinct transaction associated with the affected charge. ✅ Waived amounts are retained in transaction/reporting data. | 🟡 Partial — waiver and auditability already exist. What is not available is a dedicated charity payout lifecycle to track distribution of amounts accumulated under Charity Payable. | Reuse existing charge-waiver functionality. If BEDE requires charity distribution to be managed within LMS, add Charity Payout handling: beneficiary, amount, payout date, payment reference, evidence, approval/maker-checker and reconciliation against Charity Payable. If payout is handled by ERP/accounting, LMS may only need Charity Payable balance/reporting and integration.
25 | Rescheduling must not increase Murabaha debt/Profit. Existing contractual debt should only be redistributed over the revised tenor. Refinancing must be treated as a new Murabaha sale rather than rollover of the old debt. | ✅ Existing LMS rescheduling supports revised dates/installments and approval/rejection workflow. ✅ Product supports disabling Profit recalculation. | 🟡 Partial — the rescheduling framework exists, but conventional rescheduling can allow a new rate/recalculation. These options should not be available for Murabaha where they could increase the contractual debt. There is also no dedicated Islamic refinancing lifecycle. | For Murabaha, prevent rate changes and Profit recalculation during rescheduling and preserve the existing contractual outstanding amount while redistributing it over revised dates. Any reduction in Profit should be handled separately through Ibra'. Treat refinancing as a new Murabaha financing/sale with the required asset and sale lifecycle.
26 | Write-off and provisioning should support IFRS 9/CBB requirements and correctly distinguish recognized from unearned Murabaha Profit. | ✅ LMS supports write-off and related accounting entries. ✅ Provisioning can be configured using days overdue, provisioning percentage and mapped GL accounts. | 🟡 Partial — existing provisioning is primarily DPD/percentage-based rather than a complete IFRS 9 ECL/staging framework. Current Murabaha implementation also does not maintain a dedicated deferred/unearned Profit balance for Islamic-specific accounting treatment. | Extend/integrate provisioning where required for IFRS 9/CBB staging and ECL. Based on the approved Murabaha accounting model, introduce the required Selling Price Receivable / Deferred (Unearned) Profit treatment so write-off and recovery can appropriately distinguish financing Cost, recognized Profit, unearned Profit, fees/charity and recoveries.
F. Fees, charges and tax
35 | Permitted Murabaha fees should be limited to approved charges such as processing, documentation and actual-cost-based fees. Fees must not become disguised additional Profit, e.g. by being calculated as a % of financing/Profit. Fee income must be accounted for separately from Murabaha Profit. | ✅ LMS supports configurable charges including flat amount, % of amount, % of amount + Profit, % of Profit and % of disbursement amount. ✅ Fee income and Profit/interest income have separate GL mappings. ✅ Fees Receivable is separately supported under accrual accounting. | 🟢 Supported through configuration | Optional Sharia control/enforcement: restrict Murabaha products to approved fee codes/calculation methods and prevent users from accidentally configuring prohibited bases such as % Profit or % Amount + Profit. Where actual-cost evidence/caps are required, these can be added as additional controls.
36 | Takaful relating to the financed asset should be handled according to the approved treatment: pass-through charge, included in asset Cost before Profit calculation, or separately borne by the customer. | ✅ LMS supports configurable percentage-based charges, including charges calculated as a percentage of the finance/disbursement amount. ✅ Charges can be associated with the financing and handled separately from Profit. ✅ Separate charge accounting is available. | 🟢 Supported through configuration, subject to configuring the applicable Insurance/Takaful charge and repayment treatment. | Optional enhancement: introduce an Insurance/Takaful charge classification so it can be explicitly distinguished from normal fees in schedules, accounting, APIs and reporting. Confirm/support equal amortization of the insurance amount across the financing tenure as required by BEDE.
37 | Taxes should apply only to approved taxable fees and must not be calculated on Murabaha Profit, Selling Price/debt, Ibra', or other prohibited bases. | ✅ The TAX enhancement associates Tax Groups with Charge definitions. ✅ Tax is calculated from the underlying charge amount, rather than directly from financing Principal/Profit. ✅ Tax components support percentage/effective-date configuration. | 🟢 Supported through configuration — approved Murabaha fees can be configured with the applicable Tax Groups, while non-taxable charges/components remain without a Tax Group. | For Murabaha, restrict tax groups to approved taxable fee codes and prevent taxable charges from using prohibited calculation bases such as % Profit, % Amount + Profit, and other financing-based calculations where not permitted. Existing TAX calculation can otherwise be reused.
G. Documents and disclosures
38 | Generate Murabaha contractual documents from financing/account data, including Promise to Purchase, Purchase/Ownership Confirmation, Offer & Acceptance, Sale Contract and Repayment Schedule, with configurable templates. | ✅ Customer, financing, commodity, Cost Price, Profit, Selling Price and repayment-schedule data are already available. ✅ Repayment Schedule is already generated by the LMS. ✅ Document Management supports document storage/retrieval. ✅ Existing templating infrastructure can be reused. | 🟡 Partial — repayment schedule and required source data exist, but dedicated Murabaha contractual documents are not currently generated automatically. Templates are not currently business-configurable/versioned. | Add Murabaha document generation for Promise to Purchase, Purchase/Ownership Confirmation, Offer & Acceptance and Sale Contract using existing financing data. Add configurable/versioned templates if BEDE needs to maintain the document content without deployment.
39 | CBB Volume 5 / consumer-protection disclosure covering total financing cost, Profit, Selling Price, APR-equivalent and early-settlement/Ibra' terms. | ✅ Murabaha already maintains Cost Price, Profit and Selling Price. ✅ Repayment Schedule, fees and financing totals are available. ✅ LMS already maintains the underlying rate and repayment information required as inputs. | 🟡 Partial — core financing information exists, but there is no dedicated CBB-compliant disclosure, CBB APR-equivalent calculation or dedicated early-settlement/Ibra' disclosure. | Add CBB Consumer Disclosure using existing financing data, including the applicable APR-equivalent calculation, early-settlement/Ibra' terms and required CBB disclosure fields/wording. Generate and retain the disclosure presented to the customer.
40 | Statements and APIs show Cost/Profit split, remaining Selling Price and Ibra', using Islamic terminology rather than “interest”, including APIs consumed by BEDE's in-house application. | ✅ Murabaha already has Cost Price, Profit and Selling Price. ✅ Islamic terminology is introduced at the Murabaha financing layer. ✅ Existing APIs provide detailed schedule, balance and transaction information. | 🟡 Partial — underlying Fineract APIs still expose conventional fields such as interest, and dedicated remaining Selling Price and Ibra' fields are not fully available. Islamic terminology is therefore not yet consistent across all customer-facing statements/APIs. | Extend Murabaha statements and customer-facing APIs with explicit Cost Price, Profit, Selling Price, remaining Selling Price and Ibra' fields/labels. Ensure consuming applications receive Islamic terminology without needing to interpret conventional interest fields.
H. Shariah Governance and Audit
42 | Allow a Shariah auditor to reconstruct the complete Murabaha transaction sequence, including asset purchase/ownership, prices, offer/acceptance and timestamps, from the audit trail and supporting evidence. | ✅ Existing LMS audit captures non-read operations and relevant actors. ✅ Maker-checker provides maker/checker traceability. ✅ Murabaha captures Commodity, Supplier, Cost Price, Profit and Selling Price. ✅ Approval/disbursement events and dates are already maintained. | 🟡 Partial — general audit infrastructure exists, but the complete Murabaha ownership/sale lifecycle is not currently represented as individual auditable events. In particular, ownership/possession and offer/acceptance evidence cannot yet be reconstructed solely from the existing audit trail. We already capture a good part of the data But we don't have separate lifecycle events such as: ASSET_PURCHASED → OWNERSHIP_CONFIRMED → OFFER_CREATED → CUSTOMER_ACCEPTED → MURABAHA_SALE_EXECUTED | Extend the existing audit model with Murabaha lifecycle events, including Purchase/Ownership Confirmation, possession where applicable, Offer, Acceptance and Sale Execution. Record timestamps, actors, prices and supporting document references so the complete transaction sequence can be reconstructed for Shariah audit.
43 | Ensure conventional Fineract functionality that is not permitted for Murabaha cannot accidentally be used, and ensure future Fineract upgrades do not re-enable prohibited behaviour. | ✅ Product configuration already allows controls such as Profit Recalculation = No, floating-rate linkage disabled and no compounding. ✅ Murabaha is identified through Islamic Product / Financing Type. ✅ Existing product configuration and validation framework can be reused. | 🟡 Partial / Additional controls required — several Shariah-sensitive behaviours can already be controlled through configuration, but conventional Fineract options remain available underneath. There is not yet a complete Murabaha-specific enforcement and automated regression suite covering all prohibited combinations. The technical assessment identifies examples such as recalculation, compounding and Profit-based charges. | Add Murabaha-specific validation/enforcement for prohibited configurations and automated regression tests covering key Murabaha rules. Include these tests in the Fineract upgrade process so future upstream changes cannot silently re-enable restricted behaviour.
44 | Allow Murabaha and conventional products to coexist in the same tenant, while also supporting institutions that want to operate only Islamic products. | ✅ Already supported for coexistence: Islamic Product is configured at Loan Product level, with Financing Type = Murabaha, while conventional products remain unchanged. ✅ Islamic and conventional products can therefore coexist within the same tenant. | 🟢 Coexistence supported. 🟡 Optional control for fully Islamic institutions — there is no dedicated tenant-level Islamic Only policy identified that prevents creation/use of conventional products altogether. The supplied code assessment did not account for the Islamic Product/Financing Type customization and therefore understates the current coexistence capability. | No enhancement required for mixed coexistence. If BEDE requires a fully Islamic environment, optionally add a tenant-level Islamic Only configuration that restricts creation/activation of conventional products and hides conventional product options/actions.
E. Accounting and GL
27 | Full Murabaha accounting and journal entries across the lifecycle: asset purchase, asset holding, sale, instalment collection, Profit recognition, Ibra', charity and write-off. | ✅ Existing accounting/journal engine. ✅ GL mappings for Loan Portfolio, Fund Source, Interest/Profit Income, receivables, fees, penalties and write-off. ✅ Existing accounting events for disbursement, accrual, repayment, waiver and write-off. | 🔴 Gap — current journal entries follow the conventional loan lifecycle. There are no dedicated accounting events for Murabaha asset purchase/holding, gross sale/deferred Profit, Ibra' or charity treatment. | Add an approved Murabaha accounting/posting matrix covering the complete lifecycle, including asset purchase/holding, Murabaha sale, deferred Profit recognition, Ibra', Charity Payable and Murabaha-specific write-off treatment. Final entries/account mappings to follow BEDE's approved accounting/AAOIFI policy.
28 | At Murabaha sale, record the customer receivable according to the approved accounting treatment, including Selling Price and deferred/unearned Profit, with configurable recognition treatment where required. | ✅ Cost Price, Profit and Selling Price are available at the Murabaha financing layer. ✅ Existing LMS accounting records the financing principal/cost in Loan Portfolio and subsequently accrues Profit through the existing interest accounting model. | 🔴 Gap — Selling Price is not currently represented in accounting as a gross Murabaha receivable with separately tracked deferred/unearned Profit. | Introduce Gross Murabaha Receivable and Deferred/Unearned Murabaha Profit accounting treatment. Configure the recognition method according to BEDE's approved AAOIFI/accounting policy where multiple treatments are required.
29 | Recognise Murabaha Profit according to the approved method over the financing period, based on the fixed contractual Profit allocation, rather than conventional interest recalculation on outstanding principal. | ✅ Existing periodic accrual jobs and repayment schedule infrastructure. ✅ Murabaha already calculates/displays Profit using the existing schedule engine. ✅ Profit Recalculation can be disabled for Murabaha products. | 🟡/🔴 Partial infrastructure / Accounting enhancement required — accrual infrastructure can be reused, but accounting recognition currently follows the conventional interest-accrual model rather than a dedicated deferred Murabaha Profit balance and recognition process. | Reuse the existing accrual scheduling infrastructure but add Murabaha Profit recognition based on the approved contractual Profit allocation. Post recognition between Deferred Murabaha Profit and Murabaha Profit Income according to BEDE's approved accounting policy.
30 | Identify which existing GL roles are reused and provide dedicated Murabaha roles where required, including Inventory/Asset, Murabaha Receivable, Deferred Profit, Profit Income, Ibra' and Charity Payable. | ✅ Existing GL framework supports configurable mappings for Fund Source, Loan Portfolio, Interest/Profit Income, Fee/Penalty Income and Receivables, Write-off, Overpayment and Suspense. | 🔴 Gap — dedicated Murabaha accounting roles such as Inventory/Asset, Gross Murabaha Receivable and Deferred Profit are not currently available. Existing conventional GL roles alone do not provide the required Murabaha accounting treatment. | Extend the GL mapping model with the required Murabaha-specific account roles. Reuse existing generic roles where appropriate rather than duplicating them; e.g. existing Fund Source/Write-off/Suspense can remain where the approved accounting treatment permits.
31 | Record the asset on the balance sheet while it is owned by the institution before being sold to the customer. | ✅ Commodity, Supplier and Cost Price are captured as part of the Murabaha financing. | 🔴 Gap — commodity information is currently financing/reference data. There is no accounting event that records the purchased Murabaha asset/inventory on the balance sheet between purchase and customer sale. | Add an Asset Purchase/Ownership accounting event and Murabaha Inventory/Asset GL mapping. Record asset cost when purchased and clear the asset/inventory when the Murabaha sale is executed.
32 | When a Murabaha financing becomes non-performing, suspend Profit recognition according to the applicable DPD policy and account for suspended/reversed Profit appropriately. | ✅ LMS supports configurable overdue/NPA identification based on DPD. ✅ Existing Suspense GL capability is available. | 🔴 Gap — NPA identification exists, but it does not currently trigger a dedicated Murabaha Profit-suspension accounting treatment or stop/reverse Profit recognition according to a Murabaha policy. | Add configurable DPD-based Profit Suspension rules for Murabaha, including stopping future recognition and the required suspense/reversal accounting entries. Resume/recovery/write-off treatment should follow BEDE's approved accounting policy.
33 | Support Murabaha where asset purchase currency differs from financing currency, including exchange rate and FX accounting on the purchase leg. | ✅ LMS supports currencies at loan/account and journal-entry level. | 🔴 Gap — the current Murabaha model does not maintain a separate supplier-purchase currency/exchange-rate accounting leg or dedicated FX gain/loss treatment between asset purchase and financing. | Extend Murabaha asset purchase to capture purchase currency, financing/functional currency and applicable exchange rate, and generate the required supplier settlement, inventory and FX gain/loss entries according to BEDE's accounting policy.
34 | Export Murabaha journal entries to Odoo with the correct GL mappings and reconcile balances such as Deferred Profit between LMS and Odoo. | ✅ Existing Odoo integration exports Fineract journal entries with GL account codes, currency and amounts. ✅ Existing reconciliation identifies balanced/failed exported journals. | 🟡 Partial — the Odoo transport mechanism already exists, but the required Murabaha-specific journals/GL roles do not yet exist. Current reconciliation also does not specifically reconcile Murabaha balances such as Deferred Profit between LMS and Odoo. | Once Murabaha accounting entries and GL mappings are introduced, extend the existing Odoo integration to export them and add Murabaha balance reconciliation, particularly Gross Receivable, Deferred Profit, Inventory/Asset, Ibra' and Charity Payable.

## List Of Task to be Implemented
BEDE Murabaha – Consolidated New Requirements & Gaps
ID | Module / Capability | Requirement | Details / Controls
2 | Murabaha product and contract model | Store Cost Price, fixed Profit, Selling Price and the approved profit-allocation method as contractual values.
3 | Murabaha product and contract model | Create an immutable executed-sale snapshot so contractual values cannot change after acceptance.
4 | Murabaha product and contract model | Add product validations enforcing: | • Fixed Profit and Selling Price • Profit Recalculation = No • No floating-rate linkage • No compounding • No penalty calculated on Profit • No multiple disbursements or tranches • No prohibited fee-calculation methods
5 | Murabaha product and contract model | Optionally add a tenant-level “Islamic Only” policy preventing conventional products from being created or activated.
6 | Murabaha lifecycle and ownership | Introduce distinct controlled lifecycle states: | • Promise to Purchase • Purchase Instructed • Asset Purchased • Ownership Confirmed • Possession Confirmed • Offer Created • Customer Accepted • Murabaha Sale Executed • Receivable Active
7 | Murabaha lifecycle and ownership | Prevent offer, acceptance, sale execution and customer debt creation until asset purchase and ownership have been confirmed.
8 | Murabaha lifecycle and ownership | Record timestamps, actors and maker-checker decisions for every lifecycle transition.
9 | Murabaha lifecycle and ownership | Capture mandatory purchase evidence: | • Commodity or asset description • Supplier • Purchase price and currency • Supplier invoice/reference • Purchase date • Ownership evidence • Physical or constructive possession • Supporting documents
10 | Murabaha lifecycle and ownership | Add configurable mandatory-document and evidence rules before sale execution.
11 | Wakala and Tawarruq | Add a Wakala workflow for customer-as-agent purchases.
12 | Wakala and Tawarruq | Record the agency appointment, scope, effective dates, agent and supporting agreement.
13 | Wakala and Tawarruq | Link supplier invoices and purchase evidence to the Wakala appointment.
14 | Wakala and Tawarruq | Extend commodity integration beyond search and validation to execute or record the complete transaction chain.
15 | Wakala and Tawarruq | For Tawarruq, record each purchase and onward-sale leg, including asset, buyer, seller, prices, currencies and timestamps.
16 | Wakala and Tawarruq | Provide an audit view capable of reconstructing the complete Tawarruq transaction chain.
17 | Wakala and Tawarruq | Add adapter configuration, idempotency, retry and reconciliation controls for supported commodity platforms.
18 | Wa’d and Hamish Jiddiyyah | Model binding and non-binding Promise to Purchase classifications.
19 | Wa’d and Hamish Jiddiyyah | Add Hamish Jiddiyyah/security-deposit handling.
20 | Wa’d and Hamish Jiddiyyah | Define cancellation, actual-loss deduction, refund and accounting rules when the customer withdraws.
20 | Fixed Murabaha repayment schedule | Support Profit configuration by Rate or Fixed Amount | Add a product-level Profit Input Type configuration allowing the institution to select Profit Rate (%) or Fixed Profit Amount. When Profit Rate is selected, retain the existing rate-based calculation. When Fixed Profit Amount is selected, the Profit amount entered for the financing shall become the contractual Profit value and the system shall derive Selling Price = Cost Price + Fixed Profit Amount. The repayment schedule shall allocate the fixed Profit across installments according to the configured Profit allocation method without changing the total contractual Profit.
21 | Fixed Murabaha repayment schedule | Add a schedule engine that allocates a frozen contractual Profit amount rather than recalculating interest from balance × rate × days.
22 | Fixed Murabaha repayment schedule | Support approved allocation methods, such as straight-line or another BEDE-approved method.
23 | Fixed Murabaha repayment schedule | Ensure: | • Instalments total exactly to Selling Price • Profit portions total exactly to contractual Profit • Cost portions total exactly to Cost Price • Currency rounding is applied correctly • Final-instalment residue is controlled and auditable
24 | Fixed Murabaha repayment schedule | Ensure due-date changes and business-day adjustments never change total Profit or Selling Price.
25 | Fixed Murabaha repayment schedule | Define Murabaha-safe handling for grace periods, moratoriums, balloon payments and stepped instalments.
26 | Fixed Murabaha repayment schedule | Prohibit grace-period behaviour that increases contractual Profit.
27 | Fixed Murabaha repayment schedule | Treat top-ups and additional financing as new Murabaha contracts rather than additional disbursements against an existing sale.
28 | Early settlement and Ibra’ | Introduce an explicit Ibra’ transaction type rather than presenting it as Interest Payment Waiver. | Enhancement – reuse existing Interest Payment Waiver
29 | Early settlement and Ibra’ | Correct the current waiver allocation/journal issue so the transaction records the actual amount and generates the required journal entries. | Existing Bug – fix separately
30 | Early settlement and Ibra’ | Add configurable Ibra’ calculation rules, for example: | • Unearned Profit • Unearned Profit less administration fee • Fixed percentage • Manually approved amount • Maximum or minimum rebate rules
31 | Early settlement and Ibra’ | Add maker-checker approval for Ibra’ quotation and execution. | Enhancement – reuse existing framework
32 | Early settlement and Ibra’ | Record the calculated amount, overrides, reason, approver and calculation inputs. | New
34 | Early settlement and Ibra’ | Show Selling Price, outstanding contractual amount, Ibra’ and final settlement amount separately. | Enhancement
35 | Early settlement and Ibra’ | Replace “interest waiver” and “interest saved” terminology in customer-facing channels with approved Islamic terminology. | Enhancement
36 | Late-payment and charity management | Add a Murabaha late-payment treatment that routes applicable charges to Charity Payable rather than Penalty Income.
37 | Late-payment and charity management | Add a dedicated Charity Payable liability GL mapping.
38 | Late-payment and charity management | Restrict late-charge calculation methods according to approved Sharia rules.
39 | Late-payment and charity management | Report: | • Late charges assessed • Late charges collected • Amounts waived • Charity Payable balance • Amounts distributed • Outstanding undistributed amount
40 | Late-payment and charity management | Add a charity-payout lifecycle where managed in LMS, including beneficiary, amount, payment date, reference, evidence and approval.
41 | Late-payment and charity management | Reconcile charity payouts against the Charity Payable balance.
42 | Late-payment and charity management | Where payouts are managed in Odoo, provide the corresponding export and reconciliation interface.
43 | Rescheduling and refinancing | Add Murabaha-specific rescheduling validation that prohibits: | • Rate changes • Profit recalculation • Compounding • Increasing contractual debt • Capitalizing arrears into additional Profit
44 | Rescheduling and refinancing | Redistribute only the existing contractual outstanding amount over revised dates.
45 | Rescheduling and refinancing | Handle any Profit reduction through a separate approved Ibra’ transaction.
46 | Rescheduling and refinancing | Treat refinancing as a new Murabaha contract with a new asset purchase, ownership and sale lifecycle.
47 | Rescheduling and refinancing | Prevent conventional rollover of an existing Murabaha debt.
48 | Murabaha accounting and GL | Add an approved end-to-end Murabaha accounting posting matrix.
49 | Murabaha accounting and GL | Add dedicated GL roles for: | • Murabaha Inventory/Asset • Gross Murabaha Receivable • Deferred/Unearned Murabaha Profit • Murabaha Profit Income • Ibra’ Expense or contra-income • Charity Payable • Suspended Profit • FX Gain/Loss where applicable
50 | Murabaha accounting and GL | Add an asset-purchase accounting event: | • Dr Murabaha Inventory • Cr Cash or Supplier Payable
51 | Murabaha accounting and GL | Maintain the asset on the balance sheet between purchase and customer sale.
52 | Murabaha accounting and GL | At sale execution, record Gross Selling Price Receivable and separately track deferred Profit.
53 | Murabaha accounting and GL | Clear Murabaha Inventory when the customer sale is executed.
54 | Murabaha accounting and GL | Recognize fixed contractual Profit from Deferred Profit according to the approved accounting method.
55 | Murabaha accounting and GL | Add Murabaha-specific entries for: | • Instalment collection • Ibra’ • Late charge to Charity Payable • Charity payout • Profit suspension • Rescheduling • Write-off • Recovery after write-off
56 | Murabaha accounting and GL | Ensure write-off separates Cost, recognized Profit, unearned Profit, charity, fees and recoveries.
57 | Murabaha accounting and GL | Do not implement Murabaha accounting merely by renaming existing interest accounts.
58 | Profit suspension and impairment | Add configurable days-past-due rules for suspending Murabaha Profit recognition.
59 | Profit suspension and impairment | Stop future recognition when the suspension threshold is reached.
60 | Profit suspension and impairment | Generate approved reversal or transfer entries to Suspended Profit.
61 | Profit suspension and impairment | Define curing, recovery, resumption and write-off behaviour.
62 | Profit suspension and impairment | Extend or integrate the current DPD-percentage provisioning model with IFRS 9/CBB staging and ECL where required.
63 | Profit suspension and impairment | Retain stage, ECL inputs, results, approvals and accounting entries for audit.
64 | Multi-currency purchase and FX | Capture supplier-purchase currency separately from financing and functional currencies.
65 | Multi-currency purchase and FX | Record the applicable exchange rate, source and timestamp.
66 | Multi-currency purchase and FX | Generate inventory and supplier-settlement entries in the required currencies.
67 | Multi-currency purchase and FX | Account for realized and unrealized FX differences under BEDE’s approved policy.
68 | Multi-currency purchase and FX | Preserve the original purchase amount, converted Cost Price and exchange-rate evidence.
69 | Odoo integration and reconciliation | Export all new Murabaha journal types and GL roles to Odoo.
70 | Odoo integration and reconciliation | Map the new accounts to approved Odoo account codes.
71 | Odoo integration and reconciliation | Add balance reconciliation for: | • Murabaha Inventory • Gross Murabaha Receivable • Deferred Profit • Murabaha Profit Income • Ibra’ • Suspended Profit • Charity Payable • FX balances
72 | Odoo integration and reconciliation | Reconcile balances and transaction totals between LMS and Odoo—not only whether exported journals balance.
73 | Odoo integration and reconciliation | Add retry, idempotency and exception reporting for Murabaha accounting events.
74 | Fees, Takaful and tax controls | Add a Murabaha fee-policy configuration identifying permitted fee codes and calculation methods.
75 | Fees, Takaful and tax controls | Prevent prohibited percentage bases such as `% of Profit` or `% of Amount + Profit`.
76 | Fees, Takaful and tax controls | Where required, capture actual-cost evidence and enforce fee caps.
77 | Fees, Takaful and tax controls | Add an explicit Takaful/Insurance classification.
78 | Fees, Takaful and tax controls | Support the approved Takaful treatment: | • Pass-through charge • Separate customer charge • Capitalized into asset Cost before Profit • Institution-borne amount
79 | Fees, Takaful and tax controls | Expose Takaful separately in schedules, APIs, accounting and reports.
80 | Fees, Takaful and tax controls | Restrict tax groups to approved taxable fee codes.
81 | Fees, Takaful and tax controls | Prevent tax from being applied to Profit, Selling Price/debt, Ibra’ or charity amounts.
82 | Fees, Takaful and tax controls | Add automated validations preventing prohibited fee/tax combinations.
83 | Documents and regulatory disclosures | Generate and retain: | • Promise to Purchase • Wakala agreement, where applicable • Purchase/Ownership Confirmation • Offer and Acceptance • Murabaha Sale Contract • Repayment Schedule • Ibra’ quotation and approval • Early-settlement letter • Customer statement
84 | Documents and regulatory disclosures | Add configurable, versioned business-managed document templates.
85 | Documents and regulatory disclosures | Preserve the exact template version and generated document used for each contract.
86 | Documents and regulatory disclosures | Implement the approved CBB consumer-disclosure format.
87 | Documents and regulatory disclosures | Calculate and disclose total financing cost, Profit, Selling Price, fees, APR-equivalent and early-settlement terms.
88 | Documents and regulatory disclosures | Retain evidence of the disclosure presented to and accepted by the customer.
89 | Islamic APIs, statements and terminology | Add Murabaha-native API fields: | • Cost Price • Contractual Profit • Selling Price • Cost and Profit allocation • Remaining Selling Price • Deferred Profit • Recognized Profit • Ibra’ • Settlement Amount • Charity amounts
90 | Islamic APIs, statements and terminology | Remove conventional “interest” terminology from Murabaha customer-facing APIs, statements and documents.
91 | Islamic APIs, statements and terminology | Maintain an internal compatibility mapping where the existing calculation engine must temporarily remain.
92 | Islamic APIs, statements and terminology | Version API changes so existing conventional-product consumers are not broken.
93 | Shariah governance and audit | Obtain formal review against BEDE’s approved product manual, applicable AAOIFI standards and CBB requirements.
94 | Shariah governance and audit | Record the approving Shariah board/adviser, approval date, scope, certificate and conditions.
95 | Shariah governance and audit | Provide a Shariah audit timeline reconstructing the entire transaction from source evidence.
96 | Shariah governance and audit | Include asset, supplier, ownership, possession, offer, acceptance, prices, timestamps, actors and documents.
97 | Shariah governance and audit | Make executed-sale terms and evidence immutable or formally version-controlled.
98 | Shariah governance and audit | Record configuration changes affecting Sharia compliance through maker-checker and audit.
99 | Upgrade protection and automated assurance | Add Murabaha-specific server-side enforcement rather than depending only on users selecting the correct configuration.
100 | Upgrade protection and automated assurance | Add regression tests proving prohibited conventional behaviours cannot be activated.
101 | Upgrade protection and automated assurance | Include tests for recalculation, compounding, floating rates, tranches, Profit-based penalties, prohibited fees and debt-increasing rescheduling.
102 | Upgrade protection and automated assurance | Run the Murabaha compliance suite during every upstream Fineract upgrade.
103 | Upgrade protection and automated assurance | Add golden-ledger tests validating every Murabaha accounting event and its Odoo export.
104 | Mandatory scenario tests | Implement a 24-month on-time scenario proving: | • Schedule equals Selling Price • Cost allocations equal Cost Price • Profit allocations equal contractual Profit • Month-12 GL and Deferred Profit balances are correct
105 | Mandatory scenario tests | Implement early settlement at month 10 proving: | • Contractual outstanding amount • Ibra’ formula and approval • Resulting settlement amount • Correct journals and documents
106 | Mandatory scenario tests | Implement a 90-day-late scenario proving: | • Contractual debt does not increase • No additional Profit or compounding occurs • Late charge is routed to Charity Payable • Profit suspension follows the configured DPD policy • Odoo receives and reconciles the entries

## Murabaha Estimation
# | Module / Task | BEDE Ref. | Complexity | MD | MD |  |  | Priority | Stream
Team L2(Samer)
1 | Murabaha Profit Configuration, Fixed Profit Schedule Allocation & Rescheduling Controls | Q3-Q5, Q11-Q14, Q17, Q22, Q25 | XL | 8 | 6 | 7.8 | 62.4 | P1 |  | How Murabaha price and the repayment plan are set, and how we stop later changes (reschedule, grace, top-up) from quietly increasing the customer’s Profit or Selling Price. ALREADY DELIVERED • System already captures Cost Price, Profit, and Selling Price for Islamic/Murabaha products. • Repayment schedule already runs on the existing LMS engine. • Staff UI already supports Islamic product setup and commodity selection when creating financing. STILL TO DO • Backend: allow Profit to be entered as a fixed amount (not only a %), freeze agreed figures after sale/approval, and block unsafe product options (floating rate, compounding, multi-disbursement, profit recalculation). On reschedule, only move dates/instalments — never raise contracted Profit. • Frontend: product and financing screens for “Profit rate vs fixed amount”; hide/lock options that are not allowed for Murabaha; clear read-only totals on reschedule. WHY ESTIMATE CHANGED (8 → 6 MD) Original estimate assumed building pricing/schedule from zero. Core pricing and UI already exist; remaining work is the extra controls and fixed-amount option. AI-assisted delivery. | Add product-level Profit Input Type: 1 Profit Rate (%) 2 Fixed Profit Amount Retain existing rate-based behavior when Profit Rate is selected. When Fixed Profit Amount is selected, allow the contractual Profit amount to be entered directly. Calculate Selling Price = Cost Price + Contractual Profit. Freeze the contractual Profit once the Murabaha sale is executed. Generate the repayment schedule using the contractual Profit amount. Support approved Profit allocation method(s), including straight-line where applicable. Allocate Cost and Profit across installments. Murabaha Rescheduling & Refinancing Controls Ensure: Total Cost allocation = Cost Price Total Profit allocation = Contractual Profit Total installments = Selling Price Handle currency rounding and final-installment residue. Ensure normal due-date/business-day adjustments do not recalculate the contractual Profit. Expose Profit Input Type, contractual Profit and allocation through relevant APIs/UI. | Product config: Fixed contractual pricing / prevent floating-rate linkage Disable Profit recalculation / compounding Profit Rate vs Fixed Profit Amount validations Ensure Cost + Profit = Selling Price Prevent schedule/date changes from changing contracted Profit Multiple disbursement restrictions before/around sale execution Prevent top-up/additional financing from modifying an executed Murabaha Grace/Moratorium must not increase contractual Profit Late-payment amount must not become additional Profit Rescheduling must not recalculate/compound Profit or capitalize arrears Product/UI/API validations preventing prohibited configurations Conventional products must remain unaffected
2 | Murabaha Lifecycle, Sale Execution, Maker-Checker, Evidence & Audit Controls | Q6,Q7,Q9,Q42 | XL | 8 | 4 | 5.2 | 41.6 | P1 |  | Enforce the Sharia sequence: promise → bank buys asset → ownership/possession → offer → customer accepts → sale → only then create customer debt / disburse. Keep evidence and approvals. ALREADY DELIVERED • Full lifecycle workflow is already in the backend (separate from normal loan status). • System already blocks disbursement until Murabaha sale is completed (when the feature is switched on). • Staff portal already has a Murabaha Lifecycle tab and step screens (promise, purchase, ownership, possession, offer, acceptance, sale, cancel), plus product on/off settings. STILL TO DO • Small polish only: any remaining BEDE checklist items, clearer audit export if needed, regression after platform upgrades. • Do not rebuild this feature. WHY ESTIMATE CHANGED (8 → 4 MD) Original 8 MD was a full build. That build is already on develop. New estimate is leftover finishing work only.
3 | Ibra' & Early Settlement | Q18–Q21 | M | 3 | 2 | 2.6 | 20.8 | P1 |  | Early settlement with Ibra’ (rebate of unearned Profit): show Selling Price, rebate, and final amount clearly — not as a generic “interest waiver”. ALREADY DELIVERED • Backend Ibra’ feature is live: preview, propose, approve/reject, calculation methods, product settings. • Staff UI already has Early Settlement with Ibra’ breakdown and product configuration. STILL TO DO • Minor cleanup: wording on statements/letters, hide conventional “waive interest” where needed, any leftover journal/display fixes BEDE still flags. • Do not rebuild Ibra’. WHY ESTIMATE CHANGED (3 → 2 MD) Original assumed building Ibra’ from scratch. Most of it is already delivered; only finishing remains.
4 | Murabaha Accounting, GL, Profit Suspension & Odoo Integration | Q26–Q32, Q34 | XXL | 12 | 18 | 23.4 | 187.2 | P1 |  | Proper Islamic books: record asset while the bank owns it, then customer receivable and deferred Profit at sale, recognise Profit over time, handle Ibra’/charity/write-off correctly, and keep Odoo in sync. ALREADY DELIVERED • Standard loan accounting and Odoo export of normal journals exist. • Lifecycle and Ibra’ reuse existing disburse/waiver paths — they do not yet create full Murabaha inventory / deferred-Profit accounting. STILL TO DO • Backend: new Murabaha account roles and journal rules (inventory, gross receivable, deferred Profit, Profit income, Ibra’, charity, suspended Profit); profit suspension when seriously overdue; export to Odoo and reconcile balances (not only “journal balanced”). • Frontend: product accounting mappings for the new accounts; clearer Profit deferred vs recognised views. • Hard dependency: BEDE must approve the official posting matrix before development. WHY ESTIMATE CHANGED (12 → 18MD) Largest real gap. Original 12 was too optimistic for full AAOIFI-style accounting and Odoo reconciliation. This is also the highest risk area — careful review matters more than coding speed. | Define Murabaha-specific GL mappings and accounting treatment for asset purchase, inventory/asset holding, Murabaha sale, financing receivable, deferred/unearned Profit and Profit recognition. Support servicing entries for repayments, Ibra', late-payment/charity, rescheduling, write-off, recovery and reversals. Support Profit suspension/non-accrual for delinquent financing, including suspense/reversal and resumption on cure. Export Murabaha accounting events and GL mappings to Odoo with reconciliation, retry and idempotency controls.
5 | Takaful / Insurance Classification & Treatment | Q36 | M | 3 | 3 | 3.9 | 31.2 | P1 |  | Treat Takaful/insurance clearly (not as hidden Profit): pass-through, customer charge, add into Cost before Profit, or borne by the bank — and show it separately. ALREADY DELIVERED • Normal charges/fees framework exists (including percentage bases that Murabaha must not misuse). STILL TO DO • Backend: mark charges as Takaful; support the allowed treatments; block “% of Profit” style fees on Murabaha. • Frontend: set up Takaful on product/charges; show it separately on schedule and statements. WHY ESTIMATE CHANGED (3 → 3 MD) Unchanged — reuse existing charges with clearer classification and rules. | Reuse the existing Charges capability to classify and manage Takaful separately from normal fees and Murabaha Profit, including payment treatment, schedule/statement display, GL mapping, API and reporting.
6 | Late Payment, Charity Accounting & Management | Q22-Q24 | L | 5 | 7 | 9.1 | 72.8 | P1 |  | Late-payment amounts on Murabaha must go to charity (liability), not bank penalty income. Track what was charged, collected, waived, and paid out to charity. ALREADY DELIVERED • Normal late charges / penalties exist, but they are set up as income — not Charity Payable. STILL TO DO • Backend: Murabaha late-payment → Charity Payable account; balances and reports; optional charity payout in LMS or hand-off to Odoo; block fee methods that add hidden Profit. • Frontend: map Charity Payable on the product; reports; payout screen only if LMS owns payouts. • Decision needed: does charity payout happen in LMS or in Odoo/ERP? WHY ESTIMATE CHANGED (5 → 7 MD) Original assumed “just reuse charges”. Correct liability accounting, reporting, and payout tracking need more time. | Configure Sharia-compliant late-payment treatment without increasing Murabaha Profit; calculate and separately account for charity amounts; post to Charity Payable rather than income; track assessed/collected/waived/outstanding amounts; support charity reporting, payout recording and evidence; Maker-Checker/audit; and reconciliation with accounting/Odoo where applicable.
7 | CBB Consumer Disclosure | Q4, Q39 | M | 3 | 3 | 3.9 | 31.2 | P1 |  | CBB consumer disclosure for Murabaha: show total cost, Profit, Selling Price, fees, APR-equivalent, and early-settlement / Ibra’ terms — and keep proof the customer saw/accepted it. ALREADY DELIVERED • Cost, Profit and Selling Price already exist on the financing; Islamic labels exist in the UI. • Existing Tamam/CBB style disclosure flow can be extended rather than rebuilt. STILL TO DO • Backend: add any missing CBB fields and approved APR-equivalent calculation; store acceptance evidence. • Frontend: disclosure print/screen with Islamic wording; reuse current acceptance pattern. • Confirm exact CBB formula with compliance. WHY ESTIMATE CHANGED (3 → 3 MD) Unchanged — extend what we have; do not invent a second disclosure product. | Existing / Validation & Enhancement if required — Reuse the existing Tamam/CBB consumer disclosure flow and validate that all required Murabaha-specific fields and terminology are supported. Add only missing fields/rules.
Team L1 | [5 empty] | 0 | 0
8 | Murabaha Documents & Template Management | Q38 | XL | 8 | 6 | 7.8 | 62.4 | P1 |  | Generate and keep the official Murabaha papers (promise, ownership, offer/acceptance, sale contract, schedule, Ibra’ / early-settlement letter) from approved templates, with version history. ALREADY DELIVERED • Documents can already be stored on the financing; lifecycle can require evidence uploads. • Auto-generated, business-maintained Murabaha contract templates are not there yet. STILL TO DO • Backend: template generation at the right lifecycle step; keep exact version used; fill from financing data. • Frontend: generate/download from the lifecycle area; template admin only if business must edit wording without IT. WHY ESTIMATE CHANGED (8 → 6 MD) Document storage already exists. Remaining work is smart templates and generation, not a new document vault. | ¦ Task ¦ What is required ¦ ¦ ------------------------- ¦ ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------ ¦ ¦ **Document Templates** ¦ Configure templates for required Murabaha documents, e.g. Promise to Purchase, Purchase/Ownership evidence, Murabaha Offer, Acceptance, Sale Contract, repayment schedule, Ibra’/early-settlement statement. ¦ ¦ **Auto-population** ¦ Populate templates using LMS data: customer, asset/commodity, supplier, Cost Price, Profit, Selling Price, dates, financing terms, etc. ¦ ¦ **Document Generation** ¦ Generate the appropriate document at the relevant lifecycle stage. ¦ ¦ **Versioning** ¦ Retain the exact document/version generated and accepted for the transaction. ¦ ¦ **Storage & Retrieval** ¦ Store documents against the Murabaha account/contract and allow authorized users to retrieve them. ¦ ¦ **Acceptance / Evidence** ¦ Record acceptance/signature/reference/date where applicable. ¦ ¦ **Permissions & Audit** ¦ Control who can generate/re-generate documents and maintain an audit trail. ¦ ¦ **API** ¦ Allow relevant documents and metadata to be accessed through APIs where required. ¦
9 | Multi-Currency Purchase & FX | Q33 | XL | 5 | 7 | 9.1 | 72.8 | P1 |  | Buy the asset in one currency and finance the customer in another, with a recorded exchange rate and agreed FX profit/loss treatment. ALREADY DELIVERED • Asset purchase in the lifecycle today is mainly process/evidence — not full multi-currency inventory accounting. STILL TO DO • Backend: capture purchase currency, rate, source and time; post inventory/supplier/FX entries per policy. • Frontend: multi-currency on asset purchase; show rate evidence to users/auditors. • If Odoo owns FX accounting and LMS only stores a converted Cost Price, effort can fall to about 4–5 MD. WHY ESTIMATE CHANGED (5 → 7 MD) Original assumed a light “store converted cost” approach. Full FX accounting is more work unless ERP owns it. | if BEDE/Odoo or another external system supplies the FX rate and performs FX accounting, while LMS only receives a rate and converts/stores the Murabaha Cost Price, the scope becomes much smaller and L / ~5 MD could still be reasonable.
10 | IFRS 9 / CBB ECL Integration | Q26, Q32 | XL | 7 | 7 | 9.1 | 72.8 | P1 |  | IFRS 9 / CBB expected credit loss (ECL) and staging for Murabaha — either calculated in LMS or fed from LMS data into another system. ALREADY DELIVERED • Basic overdue / percentage provisioning only — not a full IFRS 9 ECL engine. STILL TO DO • Backend: either (A) provide Murabaha balances and delinquency data to an external ECL tool, or (B) store stages/ECL results and post provisions inside LMS. • Frontend: show stage/provision information if LMS owns the calculation. • Decision needed with BEDE: LMS calculates vs LMS only supplies data (option A is usually smaller). WHY ESTIMATE CHANGED (7 → 7 MD) Unchanged until BEDE chooses the operating model. Number can drop if they choose data-feed only. | To Validate with BEDE: Is the LMS expected to calculate and manage IFRS 9/CBB ECL and staging, or only provide the required financing data to an external ECL/accounting system? If Integration: Support or integrate with ECL calculation and credit-risk staging; provide required Murabaha balances and delinquency/default information; receive/store ECL results; maintain calculation/audit information; and generate the applicable impairment/provision GL entries and reversals in accordance with BEDE/CBB accounting requirements
11 | Wakala Workflow | Q8 | XL | 8 | 7 | 9.1 | 72.8 | P2 |  | Allow the customer to act as the bank’s agent (Wakala) to buy the asset, with a recorded agency agreement and purchase evidence. ALREADY DELIVERED • Not built yet. Current lifecycle assumes the bank purchase path; Wakala was left out of scope on purpose. STILL TO DO • Backend: new Wakala record on the financing (who is agent, period, agreement), link invoices/documents, approvals/permissions. • Frontend: product switch “Allow Wakala”; screens to create/view Wakala and upload supporting papers. • Business decision: confirm with BEDE whether Phase 1 can stay bank-buys-only (then this can wait). WHY ESTIMATE CHANGED (8 → 7 MD) Still essentially new work. Slightly lower because we can copy patterns from Lifecycle and Ibra’ already delivered.
12 | Tawarruq & Commodity Transaction Integration | Q10 | XL | 8 | 12 | 15.6 | 124.8 | P2 |  | For commodity Murabaha / Tawarruq: record the full trade chain (bank buys, then sells onward) with prices and times so a Sharia auditor can replay exactly what happened — not only “pick a commodity from a list”. ALREADY DELIVERED • Staff can search/select a commodity and attach Cost Price when creating financing. • Real broker “buy then sell” chain and full audit timeline are not implemented yet. STILL TO DO • Backend: connect to the commodity/broker platform; save each buy/sell leg; safe retries; auditor reconstruction report/API. • Frontend: show the trade timeline on the financing; simple settings for the external connection. • Dependency: BEDE must confirm which broker/platform and API — waiting on that is outside coding days. WHY ESTIMATE CHANGED (8 → 12MD) Original 8 was too low for a real external trading integration and audit trail. Higher number is more honest about integration risk.
13 | Wa'd & Hamish Jiddiyyah | Q11 | M | 3 | 5 | 6.5 | 52 | P2 |  | Promise to purchase (Wa’d): binding vs non-binding. Security deposit (Hamish Jiddiyyah): take, refund, or keep actual loss if the customer walks away — with correct accounting. ALREADY DELIVERED • “Promise to purchase” exists as a lifecycle step, with cancel and a reason. • Binding/non-binding rules and Hamish deposit money treatment are not built. STILL TO DO • Backend: classify the promise; capture Hamish amount; refund vs loss rules and ledger entries; approvals. • Frontend: fields for promise type and Hamish; cancel/refund screens that show what the customer gets back. • Needs BEDE accounting rules before build starts. WHY ESTIMATE CHANGED (3 → 5 MD) Original 3 treated this as simple forms. Money rules (deposit, loss, refund) need more careful work.
14 | Grace / Moratorium / Balloon / Step-up Structures | Q16 | S | 2 | 2 | 2.6 | 20.8 | P2 |  | Grace, holiday, balloon, or step-up repayment shapes must not increase the agreed Murabaha Profit or Selling Price. ALREADY DELIVERED • LMS already supports grace / reschedule style features for loans in general. STILL TO DO • Backend: automatic checks that contracted Profit and Selling Price stay the same after these changes; tests. • Frontend: keep current screens; use Islamic wording; warn users that totals cannot go up. WHY ESTIMATE CHANGED (2 → 2 MD) Unchanged — small control work on top of existing features. | Reuse existing Mid-term Grace Period / Loan Reschedule capability for Grace/Moratorium. Add Murabaha-specific validation to ensure schedule changes do not increase the contracted Profit or Selling Price. Balloon and Step-up structures to be supported only if required by BEDE and not already covered by existing schedule configuration.
| TOTAL |  |  | 83 | 89
| notes | All Murabaha-sensitive actions must maintain a complete audit trail including action, previous/new values or status, user/actor, date/time, Maker-Checker decision where applicable, and associated evidence/reference.
UI, API, statements and reports must expose the applicable Murabaha fields and Islamic terminology while maintaining backward compatibility with existing conventional products and integrations.
3.15

## Definitions
Feature | Example
Wakala | BEDE wants to finance a car for Petra. Instead of BEDE buying the car itself, BEDE appoints Petra as its agent (Wakeel) to purchase the car from the dealer on BEDE's behalf. Petra obtains the invoice/purchase evidence, but the purchase is for BEDE. After the required ownership/possession conditions are met, BEDE sells the car to Petra under Murabaha for Cost BHD 10,000 + Profit BHD 1,500 = BHD 11,500. The Wakala workflow manages the agency appointment and evidence that Petra acted as BEDE's agent.
Tawarruq | Petra needs BHD 10,000 cash, rather than a car or another asset for personal use. BEDE buys a commodity (for example, metal) for BHD 10,000, then sells that commodity to Petra for BHD 11,500 payable over 24 months. The commodity is then sold to another buyer for approximately BHD 10,000 cash. Petra receives the cash while owing BEDE BHD 11,500. The Tawarruq integration manages and evidences this sequence of commodity transactions.
Wa'd & Hamish Jiddiyyah | Petra asks BEDE to purchase a BHD 10,000 car so that BEDE can later sell it to her under Murabaha. Before BEDE purchases it, Petra provides a Wa'd (Promise to Purchase) and, if required, a Hamish Jiddiyyah (security deposit), for example BHD 500. If the Murabaha proceeds normally, the deposit is handled according to the agreed policy. If Petra withdraws after BEDE has incurred an actual permitted loss, the applicable amount may be deducted from the deposit and the remainder returned, according to the institution's approved rules.
Grace / Moratorium / Balloon / Step-up Structures | Support alternative Murabaha repayment structures while preserving the contracted Cost, Profit and Selling Price. Grace/Moratorium: allow agreed periods with reduced/no scheduled payment and redistribute the deferred amounts to later installments without automatically increasing contractual Profit. Balloon: allow a larger portion of the Selling Price to become due in a later/final installment. Step-up: allow installments to increase according to an agreed repayment pattern. Recalculate the payment schedule while ensuring total scheduled amounts continue to equal the contracted Selling Price, with appropriate validations, rounding and auditability.
IFRS 9 / CBB ECL Integration | Support or integrate with Expected Credit Loss (ECL) and credit-risk staging, using Murabaha balances and delinquency data to calculate/receive impairment provisions and generate the required accounting entries.

## Order of Implementation
Candidate | Suitability for first AI implementation | Why
Early Settlement & Ibra' | Recommended first | Much of the foundation already exists: Prepay Loan, Interest Payment Waiver, Recalculate Profit, maker-checker and Murabaha fields. AI needs to extend/orchestrate existing behavior rather than rewrite the lending engine.
Murabaha Lifecycle & Ownership | Good second candidate | Mostly new states, validations, evidence, timestamps and workflow. It can be modular, but it touches loan activation/debt-creation flow, so regression risk is higher.
Wa'd & Hamish Jiddiyyah | Good small candidate | Fairly isolated workflow/data extension. Good for AI, but less valuable as a demonstration because much of it is CRUD/workflow rather than financial processing.
Late Payment & Charity Management | Good later candidate | Valuable feature, but it touches charges, penalties, accounting/GL, charity liability, waiver and possibly Odoo. More dangerous as the first AI-generated change.
Documents / Islamic disclosures | Good/easier candidate | Low engine risk and modular, but it doesn't really prove AI can implement meaningful LMS financial functionality.
Fixed Murabaha Schedule Engine | Not first | Changes fundamental schedule/profit calculations. High regression and financial risk.
Murabaha Accounting / AAOIFI GL | Not first | Accounting correctness is critical and it affects journals, accruals, write-off, Odoo, reconciliation, etc.
Rescheduling / Refinancing | Not first | Interacts heavily with schedules, outstanding balances and Profit protection.
Profit Suspension / IFRS 9 | Not first | Complex accounting and delinquency interaction.

## 4
1. “Flat rate on cost”
This means the Murabaha profit is calculated directly on the original Cost Price, rather than on a reducing outstanding balance.
For example:
Cost Price = BHD 10,000
Profit rate = 5% per year flat
Tenor = 2 years
Profit = 10,000 × 5% × 2 = BHD 1,000
Selling Price = BHD 11,000
The customer owes the agreed Selling Price of BHD 11,000. The profit doesn't get recalculated each month based on the declining outstanding balance.
This is conceptually very relevant for Murabaha because the Cost Price + agreed Profit = Selling Price is established as part of the sale.
2. “Effective / annualised rate”
This is different. The effective rate is mainly a way of expressing the economic cost of the financing on an annual basis, taking into account the repayment schedule.
For example, the Murabaha contract might say:
Cost Price: BHD 10,000
Murabaha Profit: BHD 1,000
Selling Price: BHD 11,000
But because the customer is repaying the BHD 11,000 gradually over 24 months, the equivalent annual financing rate will not simply be 5%.
An effective/annualised rate is calculated from the actual cash flows—amount financed, installments, timing and potentially applicable fees—so the customer can compare the financing cost with other products.
3. Why they ask “or both?”
BEDE is asking whether FOO can maintain both concepts:
Contractual Murabaha pricing
Cost Price + Murabaha Profit = Selling Price
and separately:
Disclosure rate
Effective / Annualised Rate / APR-equivalent
So they may expect something like:
Field | Example | Purpose
Cost Price | BHD 10,000 | Asset acquisition cost
Flat Profit Rate | 5% p.a. | Murabaha pricing
Profit Amount | BHD 1,000 | Contractual profit
Selling Price | BHD 11,000 | Customer's contractual sale price
Effective/APR-equivalent | e.g. calculated % | Regulatory/customer disclosure
The key point is that the APR-equivalent does not necessarily determine the Murabaha Selling Price. It can be a calculated disclosure metric.
4. What does the CBB part mean?
Here, CBB means the Central Bank of Bahrain.
BEDE is effectively asking:
“When this Murabaha is offered to a consumer in Bahrain, can the system calculate and disclose the annualised/effective cost of financing in the format required by CBB consumer-protection rules?”
That could require defining exactly which cash flows enter the calculation—for example financing amount, installments, payment dates and applicable mandatory fees—and the calculation methodology/rounding

## 2
1. Goods Murabaha — vehicle, equipment, etc.
This is the easiest to visualize.
A customer wants to finance a specific real asset, for example a car costing AED 100,000.
The intended flow is:
Customer identifies car → Bank/financier purchases car → Bank owns car → Bank sells car to customer for Cost + Profit → Customer pays installments
Example:
Vehicle cost = 100,000
Profit = 15,000
Murabaha Selling Price = 115,000
Customer pays 115,000 over 24 months.
This is close to what our FRD currently models because we already capture Commodity, Supplier Reference, Cost Price, Profit and Selling Price.
However, our current FRD does not manage the actual bank purchase/ownership lifecycle; in fact, commodity ownership lifecycle is explicitly out of scope.
For a full goods-Murabaha implementation, configuration/data could additionally require things like asset category, supplier, purchase invoice/reference, purchase date, ownership/possession confirmation and sale execution date.
2. Commodity Murabaha / Tawarruq
This is different because the customer usually isn't financing a car or equipment they want to keep. The commodity is used as part of a structure to provide the customer with liquidity/cash financing.
A simplified flow is:
Bank buys commodity → Bank owns commodity → Bank sells commodity to customer at Cost + Profit on deferred payment → Customer sells commodity to a third party → Customer receives cash
For example:
Bank buys metals for 100,000
Bank sells them to customer for 115,000 payable over 24 months
Commodity is then sold to another broker for approximately 100,000
Customer receives the sale proceeds.
Therefore BEDE mentioning “Tawarruq via metals/commodity broker” matters. It implies much more than our current Commodity ID.
You may need to track:
Purchase broker → commodity → bank purchase → ownership confirmation → Murabaha sale → customer ownership → onward-sale broker → sale proceeds.
Our FRD currently supports connecting to a Commodity Management System to search, retrieve, validate and store commodity information. But it explicitly says the LMS does not manage commodity ownership, inventory, trading or pricing lifecycle.
So for BEDE:
Commodity selection/integration = partially aligned.
Full Tawarruq transaction chain = not currently covered.
3. Murabaha to the Purchase Orderer — MPO
This is more about the contractual process than the type of asset.
The customer first approaches the bank and says essentially:
“I want this particular vehicle/equipment/property. Please purchase it, and after you acquire it, I will buy it from you under Murabaha.”
This typically introduces a promise/request stage before the actual Murabaha sale.
Conceptually:
Customer purchase request → Promise/Wa'd → Bank purchases asset from supplier → Bank obtains ownership/possession → Bank offers asset to customer → Customer accepts → Murabaha contract is executed
This is important because the Murabaha contract should not simply exist from the moment the customer requests financing. There is a distinction between the request/promise and the later sale contract.
Our current FRD doesn't model that lifecycle. It mainly enhances the existing loan creation process with Murabaha attributes and commodity validation.
So MPO is a significant gap if BEDE requires the system to enforce and evidence these stages.

## 8
In a Wakala scenario, the bank appoints the customer as its agent to purchase the asset on the bank's behalf. So BEDE wants to know whether the LMS can prove something like:
Wakala appointment → Customer purchases on behalf of bank → Supplier invoice/purchase evidence recorded → Bank ownership established → Murabaha sale to customer
The important distinction is that the customer's purchase as agent of the bank is not yet the Murabaha sale to the customer.

## 9
Physical possession means the bank actually takes physical possession of the asset.
Constructive possession means the bank has obtained control/ownership rights over the asset even though it may not physically move through the bank's premises. For example, the asset may remain with a dealer, but ownership/control has legally passed to the bank.
BEDE's last question — “Which are mandatory before sale?” — is therefore asking whether the LMS has validation rules such as:
Murabaha Sale cannot proceed unless Supplier + Purchase Invoice + Purchase Date + Cost Price + Ownership/Possession Confirmation have been recorded.

## 36
What is Takaful?
Takaful is the Sharia-compliant alternative to conventional insurance.
In simple terms, if a bank finances an asset through Murabaha—such as a car, equipment, or property—that asset may need insurance/protection. Instead of conventional insurance, an Islamic institution may use Takaful.
For example:
Bank purchases a car for BHD 10,000
Takaful coverage costs BHD 200
Murabaha Profit = BHD 1,000
The question is: how should that BHD 200 Takaful amount be treated?
That's exactly what BEDE #36 is asking.
The three treatments mentioned by BEDE
1. Pass-through charge
The bank collects the BHD 200 from the customer and passes it to the Takaful provider.
Customer pays BHD 200 → Bank → Takaful provider
The BHD 200 is not bank fee income and not Murabaha Profit.
Our existing Charge functionality could potentially handle the collection. Accounting would need to route it appropriately rather than treating it as bank income.
2. Capitalised into Cost before Profit
The Takaful amount becomes part of the eligible acquisition cost of the asset.
For example:
Car Cost = BHD 10,000
Takaful = BHD 200
Murabaha Cost Price = BHD 10,200
Profit = BHD 1,020, assuming 10%
Selling Price = BHD 11,220
This is different because Takaful affects the Cost Price on which Murabaha Profit is calculated.
Our current Murabaha flow derives Financing Amount from the commodity Cost Price. We don't currently have a specific rule saying:
Asset Cost + eligible Takaful = Murabaha Cost Price
So this treatment would require an enhancement if BEDE needs it.
3. Separately borne by the customer
Takaful stays completely separate from the Murabaha Cost and Profit.
For example:
Cost Price = BHD 10,000
Profit = BHD 1,000
Selling Price = BHD 11,000
Takaful = BHD 200 separately
Here the BHD 200 does not increase the Cost Price used for Profit calculation.
This could potentially be represented using our existing Charge functionality.
Why did we mention provider/policy information?
If BEDE expects LMS to actually manage Takaful, they may expect information such as:
Takaful Provider: XYZ Takaful
Policy/Certificate No.: TAK-12345
Premium: BHD 200
Covered Asset: Vehicle ABC
Coverage From/To
Payment/reference
Supporting certificate