## BEDE Req vs Roadmap
BEDE LMS Scope & Requirements vs FOO Roadmap (Summary Of Tasks) — Consolidated Traceability
"Summary Of Tasks" = FOO roadmap of known gaps to be built. Each BEDE requirement is checked: is it in the roadmap, does the roadmap item need BEDE details added (column K), is it missing from the roadmap, or is it already native. Bottom section = roadmap items BEDE does not require or that contradict BEDE. Roadmap # follows Summary Of Tasks numbering (#10.x / #11.x = Islamic Financing sub-rows).
Status | Count | Meaning |  | KEY FINDINGS
In Roadmap | 6 | Roadmap item exists and matches the BEDE requirement |  | 1. Missing from roadmap (product features): product versioning + SSB approval gate (FR-05/06), disbursement to CBS/merchant (FR-16), top-up (FR-20), customer statements (FR-25), collections queues & promise-to-pay (FR-30), SSO/MFA (FR-31/INT-10), DWH read replica/CDC (FR-35/INT-09), bureau reporting (INT-06), AML/sanctions hooks (INT-07), batch-job alerting (FR-39). | [11 empty] | In Roadmap
In Roadmap – add BEDE details | 33 | Roadmap item exists – BEDE asks for more; add the details in column K to the roadmap item |  | 2. In roadmap but BEDE asks for more (add col K details): schedule templates incl. skip/seasonal/step-down (#11.7), in-app e-sign (#11.1), ibra' on partial settlement (#10.3), LMS-vs-CBS recon (#21), WhatsApp + delivery status (#16), all §4.3 journeys in app API (#1), migration scope M-02..M-08 (#36). | [11 empty] | In Roadmap – add BEDE details
Missing from Roadmap | 27 | BEDE requirement with no roadmap item and not native – new roadmap item needed |  | 3. Conflicts: #9 one active loan vs FR-21; #27 partial payment held vs FR-19; Mambu option vs NFR-06/17/19; C-01 IP clause vs FOO reusable Murabaha modules. | [11 empty] | Missing from Roadmap
Conflicts with Roadmap item | 8 | Roadmap item (or option) contradicts the BEDE requirement |  | 4. Roadmap items not required by BEDE (exclude from BEDE estimate, ≈ 40 MD): #2, #4, #5 (engine out of scope §3.2), #10.4 Takaful, #11.2 FX, #11.4 Wakala, #18, #19, #20, #22, #23, #24. | [11 empty] | Conflicts with Roadmap item
Native – no roadmap item needed | 4 | Already available in Fineract/FOO – configuration only |  | 5. Build location (cols K–L): Inside Mifos = product versioning, SSB gate, data retention/purge, plus conflict fixes #9/#27. Outside Mifos = collections tool, bureau reporting, DWH/CDC, IdP, integration middleware, DevOps/monitoring. Split = disbursement, top-up, statements, AML hooks, SSO, logging/telemetry, zero-downtime/rollback. | [11 empty] | Native – no roadmap item needed
Non-roadmap (delivery / support / commercial) | 43 | Not a product feature: delivery, NFR process, support or commercial – plan/price in the response |  | 6. Not estimated yet: #3, #4, #31–#35; non-roadmap effort (QA/SIT, perf & pen test, DevOps/IaC, docs, training, discovery, PM, hypercare) to add to the BEDE response. | [11 empty] | Non-roadmap (delivery / support / commercial)
Roadmap only – not required by BEDE | 12 | Roadmap item not required by BEDE – keep in product roadmap, exclude from BEDE estimate | [13 empty] | Roadmap only – not required by BEDE
Roadmap – rescope to BEDE wording | 3 | Roadmap item related, but must be reshaped to BEDE requirement | [13 empty] | Roadmap – rescope to BEDE wording
Roadmap – keep (implied by CBB) | 2 | Not explicit in BEDE doc, but needed for a CBB-licensed lender | [13 empty] | Roadmap – keep (implied by CBB)
Total | 138 | 118 BEDE requirements + 20 roadmap-only items (no BEDE requirement)
Ref ID | Source | Category | BEDE Section | BEDE Requirement | Roadmap Item # | Roadmap Item (Summary Of Tasks) | Roadmap Estimate (MD) | Phase | Status | Build Location (Missing / Conflict items) | What Goes Inside Mifos vs Outside | BEDE Details to Add to Roadmap Item / New Item | Fineract / FOO Platform Baseline | Gap / What to Check | Recommended Action
FR-01 | BEDE Scope | Functional | 4.1 Product configuration | Fully configurable Sharia-compliant financing products with no code changes: term, min/max amount, profit rate, fees, repayment frequency, grace periods, eligibility tags. | #29, #10.1, #11.7 | #29 Business & System Configuration Management #10.1 Murabaha Profit Configuration, Fixed Profit Schedule Allocation & Rescheduling Controls #11.7 Grace / Moratorium / Balloon / Step-up Structures | #29: 5 + #10.1: 6 + #11.7: 2 | P1 | In Roadmap – add BEDE details | — | — | #29: products configurable with no code – term, min/max amount, profit rate, fees, repayment frequency, grace periods. NEW: eligibility tags on product. | Native: term, min/max, rate, fees, frequency, grace are standard Fineract product settings. | "Eligibility tags" on products are not in any roadmap item and are not native. | Add product eligibility-tag attribute that the Eligibility Engine output can match against (ties to FR-02 / INT-02).
FR-02 | BEDE Scope | Functional | 4.1 Product configuration | Product variants driven by type of good financed, customer nationality, credit report outcome, and any other attribute exposed by the Eligibility Engine. | #6 | #6 Risk-Band-Based Product Eligibility & Offer Determination | #6: 5 | P1 | In Roadmap – add BEDE details | — | — | #6: variants driven by type of good financed, customer nationality, credit report outcome and any attribute exposed by BEDE Eligibility Engine (not only FOO score/risk band). | Custom build. | Task #6 decides products by FOO score/risk band. BEDE wants variants driven by attributes from THEIR Eligibility Engine (goods type, nationality, bureau outcome). | Rescope #6 to a generic attribute-to-product rule mapping fed by the BEDE engine; re-estimate.
FR-03 | BEDE Scope | Functional | 4.1 Product configuration | Customisable, reusable repayment schedule templates incl. irregular patterns (pay one month, skip two), bullet, step-up/step-down, seasonal. | #11.7 | #11.7 Grace / Moratorium / Balloon / Step-up Structures | #11.7: 2 | P1 | In Roadmap – add BEDE details | — | — | #11.7: reusable, customisable schedule templates; irregular patterns (pay 1 month / skip 2), bullet, step-up AND step-down, seasonal. | Partial: Fineract supports variable instalments & re-amortisation but no reusable schedule templates; skip/seasonal patterns are custom. | #11.7 (2 MD) covers grace/balloon/step-up only. Reusable templates, skip-N-months and seasonal patterns are not covered. | Add "Schedule template engine" task; 2 MD is very likely underestimated.
FR-04 | BEDE Scope | Functional | 4.1 Product configuration | Configurable repayment allocation order (fees/profit/principal), day-count convention, rounding rules, weekend & public-holiday handling. | #27, #29 | #27 EMI schedule, oldest-unpaid-first allocation, partial repayment held until full EMI #29 Business & System Configuration Management | #27: 2.5 + #29: 5 | P1, P2 | Native – no roadmap item needed | — | — | Configure: allocation order fees/profit/principal, day-count, rounding, weekend & public-holiday handling. | Native: payment allocation strategies, days-in-year/month, currency rounding, holidays & working days. | Validate holiday/weekend shifting behaves correctly with fixed Murabaha profit (no extra profit on shifted dates). | Configuration + validation only.
FR-05 | BEDE Scope | Functional | 4.1 Product configuration | Product versioning: changes apply to new contracts only unless explicitly migrated; full history retained. | — | — | — | — | Missing from Roadmap | Inside Mifos / Fineract | Fineract loan-product module: product version entity, version history, "apply to new contracts only" + controlled migration; Mifos web UI screens. | NEW roadmap item: Product versioning: changes apply to new contracts only unless explicitly migrated; full history retained. | Partial: existing loans keep their terms, but Fineract has no product version entity or version history. | No roadmap item covers product versioning or explicit migration of contracts to a new version. | Add task: product version model + history + controlled migration of existing contracts.
FR-06 | BEDE Scope | Functional | 4.1 Product configuration | Sharia Supervisory Board approval recorded against each product version as an acceptance gate before activation. | — | — | — | — | Missing from Roadmap | Inside Mifos / Fineract | Fineract: product status Draft → SSB-Approved → Active, approval record (approver, date, document) per version, activation blocked without it; Mifos UI. | NEW roadmap item: Sharia Supervisory Board approval recorded against each product version as an acceptance gate before activation. | Custom build. | Not in roadmap. Depends on FR-05 versioning. (#10.2 maker-checker is contract-level, not product-level.) | Add task: SSB approval record + activation gate per product version.
FR-07 | BEDE Scope | Functional | 4.2 Murabaha mechanics | Explicit Murabaha contract model: cost price, profit amount, total sale price; commodity purchase then sale to customer. | #10.1, #10.2, #11.5 | #10.1 Murabaha Profit Configuration, Fixed Profit Schedule Allocation & Rescheduling Controls #10.2 Murabaha Lifecycle & Sale Execution Controls, Maker-Checker, Audit & Evidence #11.5 Tawarruq & Commodity Transaction Integration | #10.1: 6 + #10.2: 4 + #11.5: 12 | P1 | In Roadmap | — | — | #10.1/#10.2/#11.5: explicit cost price, profit amount, total sale price; commodity purchase then sale to customer. | FOO Murabaha scope (custom on Fineract). | Covered by Islamic Financing core + commodity integration. | Keep.
FR-08 | BEDE Scope | Functional | 4.2 Murabaha mechanics | Murabaha sale contract & offer/acceptance documents in Arabic and English, presented and e-signed in the app before disbursement, stored with the loan record. | #11.1, #10.7 | #11.1 Murabaha Documents & Template Management #10.7 CBB Consumer Disclosure | #11.1: 6 + #10.7: 3 | P1 | In Roadmap – add BEDE details | — | — | #11.1: Murabaha sale contract + offer/acceptance documents in Arabic & English; presented and e-signed in the app before disbursement; stored with the loan record. | Native document storage; templates/e-sign custom. | #11.1 covers templates. In-app presentation + e-signature capture + gate "no disbursement before signature" is not explicit. | Add e-signature/acceptance capture via mobile app (INT-01) and a pre-disbursement gate.
FR-09 | BEDE Scope | Functional | 4.2 Murabaha mechanics | Profit recognition rules configurable per product; no compounding of profit; late payment charges routed to a designated charity account, not income. | #10.5, #10.6 | #10.5 Late Payment & Charity Accounting, Management #10.6 Murabaha Accounting, GL, Profit Suspension & Odoo Integration | #10.5: 7 + #10.6: 18 | P1 | In Roadmap | — | — | #10.5/#10.6: profit recognition configurable per product; no compounding; late charges to designated charity account, not income. | Custom (FOO Murabaha). | Covered. | Keep.
FR-10 | BEDE Scope | Functional | 4.2 Murabaha mechanics | Profit rebate (ibra') rules configurable per product for early AND partial settlement. | #10.3, #15 | #10.3 Ibra' & Early Settlement #15 Early Settlement Interest / Profit Adjustment | #10.3: 2 + #15: 2 | P1, P2 | In Roadmap – add BEDE details | — | — | #10.3/#15: ibra' rules configurable per product for early AND partial settlement. | Custom. | #10.3 / #15 cover ibra' on early settlement. Ibra' on PARTIAL settlement is not explicit. | Extend #10.3 to partial settlement (links to FR-19).
FR-11 | BEDE Scope | Functional | 4.2 Murabaha mechanics | Full accounting sub-ledger: chart of accounts, automated journal postings for every financial event, month-end & year-end close, audit-ready trial balance. | #10.6 | #10.6 Murabaha Accounting, GL, Profit Suspension & Odoo Integration | #10.6: 18 | P1 | In Roadmap – add BEDE details | — | — | #10.6: chart of accounts, automated postings for every financial event, month-end AND year-end close, audit-ready trial balance. | Native: CoA, auto-posting, accounting closure, trial balance. | Validate year-end close (P&L to retained earnings) – Fineract closure is period lock only. | Validate year-end process; may need a small task.
FR-12 | BEDE Scope | Functional | 4.2 Murabaha mechanics | IFRS 9 / AAOIFI staging & provisioning outputs (DPD, stage classification, ECL inputs) per loan and portfolio. | #11.3, #31 | #11.3 IFRS 9 / CBB ECL Integration #31 AAOIFI / FAS Reporting | #11.3: 7 + #31: N/A | P1, P2 | In Roadmap – add BEDE details | — | — | #11.3/#31: per loan & portfolio – DPD, stage classification, ECL inputs (IFRS 9 / AAOIFI). | Partial native (provisioning), staging/ECL custom. | #31 AAOIFI/FAS reporting has no estimate (N/A). | Estimate #31.
FR-13 | BEDE Scope | Functional | 4.2 Murabaha mechanics | Daily automated reconciliation of the LMS sub-ledger against the Core Banking System with exception reporting. | #21 | #21 External Repayment & Bank Reconciliation Integration | #21: 10 | P1 | In Roadmap – add BEDE details | — | — | #21: daily automated reconciliation of LMS sub-ledger vs Core Banking System, with exception reporting. | Custom. | #21 is payment-gateway/bank reconciliation. LMS-vs-CBS GL reconciliation and the exception report are not explicit. | Extend #21 or add a dedicated CBS reconciliation + exception report task.
FR-14 | BEDE Scope | Functional | 4.3 Loan lifecycle | Application from the app; LMS receives eligibility output and returns eligible products, terms and indicative schedules. | #3, #6, #17 | #3 Borrower Eligibility Check & Decisioning API #6 Risk-Band-Based Product Eligibility & Offer Determination #17 LMS Loan Origination & Status Workflow Enhancements | #3: not estimated + #6: 5 + #17: 3 | P1 | In Roadmap – add BEDE details | — | — | #3/#6/#17: LMS receives eligibility output from BEDE engine; returns eligible products, terms and indicative schedules to the app. | Native: schedule preview (calculate-schedule API). Product filtering custom. | Tasks #3/#6 assume FOO decides eligibility. BEDE: the LMS CONSUMES the in-house engine output (engine is out of scope §3.2). INT-02 direction still TBD. | Rescope #3 to "consume eligibility output → return products/terms/indicative schedule". Close INT-02 TBD first.
FR-15 | BEDE Scope | Functional | 4.3 Loan lifecycle | Approval workflow with configurable stages, maker-checker, and automated approval where rules permit. | #17 | #17 LMS Loan Origination & Status Workflow Enhancements | #17: 3 | P1 | In Roadmap – add BEDE details | — | — | #17: configurable approval stages, maker-checker, automated approval where rules permit. | Native maker-checker; multi-stage approval and rule-based auto-approval are custom. | #17 covers status workflow, not configurable approval stages or auto-approval rules. | Add/extend: configurable approval stages + auto-approve rules.
FR-16 | BEDE Scope | Functional | 4.3 Loan lifecycle | Disbursement to customer account or merchant/commodity counterparty, status tracked against Core Banking confirmation. | #11.5 | #11.5 Tawarruq & Commodity Transaction Integration | #11.5: 12 | P1 | Missing from Roadmap | Split – Mifos + outside | Mifos: disbursement state "pending CBS confirmation", payee type (customer / merchant / commodity counterparty), business events. Outside: integration adapter that calls the CBS payout and returns the confirmation callback. | NEW: disbursement to customer account or merchant/commodity counterparty; status tracked against Core Banking confirmation. | Custom (Optasia comparison: external disbursement & callback = Custom Build). | No roadmap item for outbound disbursement to CBS / merchant and confirmation tracking. #21 is inbound only. | Add task: CBS disbursement integration (merchant/counterparty payout + confirmation callback).
FR-17 | BEDE Scope | Functional | 4.3 Loan lifecycle | Repayment via the app through integrated payment gateways; repayments received through Core Banking also matched and applied. | #21, #27 | #21 External Repayment & Bank Reconciliation Integration #27 EMI schedule, oldest-unpaid-first allocation, partial repayment held until full EMI | #21: 10 + #27: 2.5 | P1, P2 | In Roadmap | — | — | #21/#27: repayment via app through payment gateways; repayments received via Core Banking matched and applied. | Native repayment posting; gateway/CBS matching custom. | Covered by #21. | Keep.
FR-18 | BEDE Scope | Functional | 4.3 Loan lifecycle | Early settlement configurable per product: without profit, with profit, fixed fee, or % of settled amount. Settlement quote generated in-app. | #12, #13, #14, #15, #10.3 | #12 Early Settlement Event / Trigger Support #13 Early Settlement Fee / Charge Support #14 Early Settlement Fee Waiver #15 Early Settlement Interest / Profit Adjustment #10.3 Ibra' & Early Settlement | #12: 2 + #13: 3 + #14: 2 + #15: 2 + #10.3: 2 | P1, P2 | In Roadmap – add BEDE details | — | — | #12–#15: options per product – settle without profit / with profit / fixed fee / % of settled amount; settlement quote generated in-app. | Native payoff quote; fee/profit options custom. | Fee "as % of settled amount" option to be confirmed in #13. In-app quote depends on INT-01. | Keep; confirm % option.
FR-19 | BEDE Scope | Functional | 4.3 Loan lifecycle | Partial payment with the same charging options as FR-18 and automatic schedule recalculation. | #27 | #27 EMI schedule, oldest-unpaid-first allocation, partial repayment held until full EMI | #27: 2.5 | P2 | Conflicts with Roadmap item | Inside Mifos / Fineract | Fineract: replace #27 behaviour – apply partial prepayment, charge options per FR-18, re-amortise / recalculate Murabaha schedule. | #27 → change to: partial payment applied immediately with the same charge options as FR-18 + automatic schedule recalculation. | Native partial prepayment with re-amortisation. | #27 HOLDS partial repayments until a full EMI is reached — the opposite of BEDE (apply partial prepayment, charge per FR-18, recalc schedule). | Replace #27 behaviour with partial-prepayment + charge options + schedule recalculation.
FR-20 | BEDE Scope | Functional | 4.3 Loan lifecycle | Loan top-up with configurable eligibility, re-underwriting via Eligibility Engine, treated as new or consolidated contract per product. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: Murabaha top-up as new or consolidated contract (closing old balance, new sale price, accounting). Outside: re-underwriting call to BEDE Eligibility Engine via integration layer. | NEW roadmap item: Loan top-up with configurable eligibility, re-underwriting via Eligibility Engine, treated as new or consolidated contract per product. | Native top-up exists for conventional loans; Murabaha consolidation is custom. | Not in roadmap. | Add task: Murabaha top-up (new vs consolidated contract) + re-underwriting call.
FR-21 | BEDE Scope | Functional | 4.3 Loan lifecycle | Multiple concurrent finances per customer, with portfolio-level exposure limits configurable per product and customer segment. | #9 | #9 Enforce one active loan per customer | #9: 1 | P1 | Conflicts with Roadmap item | Inside Mifos / Fineract | Fineract: allow multiple active loans; exposure-limit check per product & customer segment at application/approval. | #9 → change to: multiple concurrent finances per customer + exposure limits configurable per product and customer segment. | Native: multiple loans per client. Exposure limits custom. | #9 ENFORCES ONE active loan per customer — contradicts BEDE requirement. | Replace #9 with configurable exposure limits per product/segment.
FR-22 | BEDE Scope | Functional | 4.3 Loan lifecycle | Deferment for a configurable number of days/months, with limits per product and configurable treatment of profit during deferment. | #11.7, #10.1 | #11.7 Grace / Moratorium / Balloon / Step-up Structures #10.1 Murabaha Profit Configuration, Fixed Profit Schedule Allocation & Rescheduling Controls | #11.7: 2 + #10.1: 6 | P1 | In Roadmap – add BEDE details | — | — | #11.7/#10.1: deferment for configurable days or months; limits per product; configurable profit treatment during deferment. | Native loan reschedule; limits per product custom. | #11.7 covers moratorium at origination; post-disbursement customer deferment with per-product limits not explicit. | Extend #10.1 rescheduling controls to deferment rules.
FR-23 | BEDE Scope | Functional | 4.3 Loan lifecycle | Restructuring and rescheduling (staff-initiated) with maker-checker approval and full audit trail. | #10.1 | #10.1 Murabaha Profit Configuration, Fixed Profit Schedule Allocation & Rescheduling Controls | #10.1: 6 | P1 | In Roadmap | — | — | #10.1: staff-initiated restructuring/rescheduling with maker-checker and full audit trail. | Native reschedule + maker-checker. | Covered. | Keep.
FR-24 | BEDE Scope | Functional | 4.3 Loan lifecycle | Write-off, fee waiver, refund and overpayment handling with maker-checker approval. | #28, #14 | #28 Partial & Full Loan Write-Off #14 Early Settlement Fee Waiver | #28: 2 + #14: 2 | P2 | In Roadmap – add BEDE details | — | — | #28/#14: partial & full write-off, fee waiver, refund, overpayment handling – all with maker-checker. | Native: write-off, waive charge, overpayment/credit-balance refund, maker-checker. | #28 write-off (partial write-off to validate); #14 is early-settlement waiver only. General waiver/refund/overpayment not listed (likely native). | Validate native waiver/refund/overpayment for Murabaha; no new task expected.
FR-25 | BEDE Scope | Functional | 4.3 Loan lifecycle | Customer statements, repayment schedules and settlement quotes on demand from the app and the back-office console. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: statement data (transactions, schedule, payoff quote APIs – mostly native). Outside: statement rendering (AR/EN PDF) in a document/reporting service and exposure to the app via the mobile backend. | NEW roadmap item: Customer statements, repayment schedules and settlement quotes on demand from the app and the back-office console. | Native schedule & payoff; customer statement generation is not native. | No roadmap item for statement generation (PDF/AR-EN) and exposure to app. | Add task: customer statement generation + app API.
FR-26 | BEDE Scope | Functional | 4.4 Collections & defaults | Default & delinquency rules configurable per product (DPD thresholds, amount thresholds, missed instalment count). | #26, #35 | #26 90+ DPD Profit Accrual Suspension #35 Aging & Delinquency Reporting | #26: 2.5 + #35: N/A | P2 | In Roadmap – add BEDE details | — | — | #26/#35: default/delinquency rules per product – DPD thresholds, amount thresholds, missed-instalment count. | Native DPD delinquency buckets; amount-threshold & missed-count rules custom. | No roadmap item for amount / missed-count rules (#35 is reporting only). | Add small task or validate config.
FR-27 | BEDE Scope | Functional | 4.4 Collections & defaults | Delinquency staging (pre-due reminder, 1–30, 31–60, 61–90, 90+, legal) with configurable names, thresholds and actions. | #16, #35 | #16 Loan Notifications & Reminder Orchestration #35 Aging & Delinquency Reporting | #16: 4 + #35: N/A | P1, P2 | In Roadmap – add BEDE details | — | — | #16/#35: stages pre-due reminder, 1–30, 31–60, 61–90, 90+, legal – configurable names, thresholds and actions. | Native buckets with names/ranges; stage-driven actions & pre-due stage custom. | Stage "actions" (trigger notification/queue/legal) not covered. | Link delinquency stages to #16 notifications and FR-30 queues.
FR-28 | BEDE Scope | Functional | 4.4 Collections & defaults | Automated notifications to customers and internal teams, templates configurable per product, per stage, per channel. | #16 | #16 Loan Notifications & Reminder Orchestration | #16: 4 | P1 | In Roadmap | — | — | #16: notifications to customers AND internal teams; templates per product, per stage, per channel. | Partial native (hooks/events); orchestration custom. | Internal-team notifications to confirm in #16. | Keep.
FR-29 | BEDE Scope | Functional | 4.4 Collections & defaults | Channels: SMS, push, email, WhatsApp; Arabic & English; delivery status tracked. | #16 | #16 Loan Notifications & Reminder Orchestration | #16: 4 | P1 | In Roadmap – add BEDE details | — | — | #16: channels SMS, push, email, WhatsApp; Arabic & English; delivery status tracked. | Custom. | WhatsApp channel and delivery-status tracking not explicit in #16. | Extend #16.
FR-30 | BEDE Scope | Functional | 4.4 Collections & defaults | Collections work queues in back-office console, promise-to-pay tracking and contact history. | — | — | — | — | Missing from Roadmap | Outside Mifos | Recommended outside: collections tool/CRM (work queues, promise-to-pay, contact history) fed by Fineract delinquency events & APIs. Alternative: custom Mifos module (larger effort). | NEW roadmap item: Collections work queues in back-office console, promise-to-pay tracking and contact history. | Not native (notes only). | Not in roadmap. Also not in Optasia comparison. | Add task: collections queues + PTP + contact history (or integrate a collections tool).
FR-31 | BEDE Scope | Functional | 4.5 Back-office console | Role-based access control with SSO (SAML/OIDC) and MFA; segregation of duties enforced. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Outside: identity provider (Keycloak or Bede IdP) for SAML/OIDC + MFA. Mifos: Fineract configured as OAuth2/OIDC resource server; roles & segregation-of-duties matrix in Fineract RBAC. | NEW roadmap item: Role-based access control with SSO (SAML/OIDC) and MFA; segregation of duties enforced. | Native RBAC & 2FA; SSO via OAuth2/OIDC is configurable but needs integration. | No roadmap item for SSO/IdP integration (INT-10). | Add task: SSO (SAML/OIDC) + MFA + SoD role design.
FR-32 | BEDE Scope | Functional | 4.5 Back-office console | Maker-checker on all configuration changes and financial adjustments. | #29 | #29 Business & System Configuration Management | #29: 5 | P1 | Native – no roadmap item needed | — | — | No roadmap item – configure during implementation. | Native maker-checker per permission. | Configuration only. | Configure during implementation.
FR-33 | BEDE Scope | Functional | 4.5 Back-office console | Immutable audit trail of every configuration change, data change and user action, exportable for Internal Audit and CBB. | #7 | #7 Persist decisioning snapshot for audit and care portal | #7: 1.5 | P1 | In Roadmap – add BEDE details | — | — | #7: immutable audit trail of every config change, data change and user action; exportable for Internal Audit and CBB. | Native command audit for write actions; read/view actions and export are not complete. | #7 is decision snapshot only. Full user-action audit + export not covered. | Add task: audit completeness + export.
FR-34 | BEDE Scope | Functional | 4.5 Back-office console | Customer 360: profile, contracts, schedules, payments, communications, documents. | #7 | #7 Persist decisioning snapshot for audit and care portal | #7: 1.5 | P1 | In Roadmap – add BEDE details | — | — | #7: Customer 360 – profile, contracts, schedules, payments, communications, documents. | Native client view (profile, loans, schedule, payments, documents). | Communications history is missing (depends on #16 logging). | Add communications log to client view.
FR-35 | BEDE Scope | Functional | 4.6 Reporting & data | Analytics access to structured loan data with zero impact on transactional system via read replica or CDC feed to Bede DWH. | — | — | — | — | Missing from Roadmap | Outside Mifos | Bede AWS: RDS read replica or CDC (e.g. Debezium/DMS) to Bede data warehouse. No Fineract change; FOO provides schema & data dictionary. | NEW roadmap item: Analytics access to structured loan data with zero impact on transactional system via read replica or CDC feed to Bede DWH. | Not native (infra). | Not in roadmap. | Add task: read-replica / CDC (e.g. Debezium) feed spec; coordinate with Bede AWS.
FR-36 | BEDE Scope | Functional | 4.6 Reporting & data | Full data model documentation: ERD and data dictionary, maintained across releases. | — | — | — | — | Missing from Roadmap | Outside Mifos | Documentation deliverable (ERD + data dictionary of Fineract + custom tables), maintained per release. | NEW roadmap item: Full data model documentation: ERD and data dictionary, maintained across releases. | Deliverable. | No roadmap item / effort. | Add documentation effort.
FR-37 | BEDE Scope | Functional | 4.6 Reporting & data | Structured extracts to support CBB regulatory returns and Sharia audit. | #34, #31 | #34 Regulatory Reporting – CBB #31 AAOIFI / FAS Reporting | #34: N/A + #31: N/A | P2 | In Roadmap – add BEDE details | — | — | #34/#31: structured extracts for CBB regulatory returns and Sharia audit. | Custom reports. | #34 and #31 are not estimated (N/A). | Estimate #31/#34.
FR-38 | BEDE Scope | Functional | 4.6 Reporting & data | Operational reports: portfolio, disbursements, collections, delinquency aging, settlements, profit recognised. | #30, #32, #33, #35 | #30 Real-Time Management & Financial Dashboards (profit/yield/deferred profit/aging) #32 Deferred / Unearned Profit Movement Report #33 Receivable Balance Movement Report #35 Aging & Delinquency Reporting | #30: 2 + #32: N/A + #33: N/A + #35: N/A | P2 | In Roadmap – add BEDE details | — | — | #30/#32/#33/#35: portfolio, disbursements, collections, delinquency aging, settlements, profit recognised. | Existing LMS dashboard covers portfolio/delinquency/collections (see Dashboard requirements tab). | Settlements report not explicit; #32/#33/#35 not estimated. | Add settlements report; estimate reports.
FR-39 | BEDE Scope | Functional | 4.7 Batch processing | EOD & periodic jobs (accruals, aging, provisioning, dunning, schedule generation) monitored, idempotent, re-runnable, alerting on failure. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: COB/scheduler jobs expose status & metrics (mostly native; idempotency to verify for custom Murabaha jobs). Outside: monitoring stack (CloudWatch/Prometheus) alert rules on job failure. | NEW roadmap item: EOD & periodic jobs (accruals, aging, provisioning, dunning, schedule generation) monitored, idempotent, re-runnable, alerting on failure. | Native COB/scheduler jobs; failure alerting is not native. | No roadmap item for job monitoring/alerting. | Cover under NFR-14/15 observability task.
INT-01 | BEDE Scope | Integration | 5 Integrations | Mobile application & existing mobile backend (built by Foo) – bi-directional, all customer journeys in §4.3. | #1 | #1 Partner API / Facade (Tamam-facing REST replacing Optasia) | #1: 6 | P1 | In Roadmap – add BEDE details | — | — | #1: bi-directional with Bede mobile app & mobile backend (built by FOO) covering ALL §4.3 journeys – application, approval, disbursement, repayment, early & partial settlement quote, top-up, deferment, statements, e-sign. | Custom. | #1 is framed as a Tamam/Optasia-replacement facade. Confirm it covers ALL §4.3 journeys: top-up, deferment, partial payment, statements, e-sign, quotes. | Re-scope #1 to the full §4.3 journey list; re-estimate.
INT-02 | BEDE Scope | Integration | 5 Integrations | Eligibility Engine (in-house) – inbound to LMS. Direction TBD: engine sends outcome & LMS returns products, OR LMS returns all products & engine filters. | #3, #6 | #3 Borrower Eligibility Check & Decisioning API #6 Risk-Band-Based Product Eligibility & Offer Determination | #3: not estimated + #6: 5 | P1 | In Roadmap – add BEDE details | — | — | #3/#6: Eligibility Engine → LMS. Direction TBD: (a) engine sends outcome, LMS returns eligible products & terms, or (b) LMS returns all products, engine filters. | Custom. | Open TBD in BEDE doc. Engine itself is OUT of scope (§3.2) – see task-only rows #2, #4, #5. | Close the TBD with BEDE before estimating #3/#6.
INT-03 | BEDE Scope | Integration | 5 Integrations | Commodity platform – bi-directional; purchase & sale confirmation for Sharia compliance. | #11.5 | #11.5 Tawarruq & Commodity Transaction Integration | #11.5: 12 | P1 | In Roadmap | — | — | #11.5: bi-directional – commodity purchase and sale confirmation for Sharia compliance. | Custom. | Covered (12 MD). | Keep; need commodity provider API docs.
INT-04 | BEDE Scope | Integration | 5 Integrations | Payment gateways – inbound; repayment status, reconciliation, refunds. | #21 | #21 External Repayment & Bank Reconciliation Integration | #21: 10 | P1 | In Roadmap – add BEDE details | — | — | #21: inbound – repayment status, reconciliation, refunds. | Custom. | Refund flow to confirm in #21. | Keep.
INT-05 | BEDE Scope | Integration | 5 Integrations | Core Banking System – bi-directional; disbursement fund movement, repayment detection, daily reconciliation. | #21 | #21 External Repayment & Bank Reconciliation Integration | #21: 10 | P1 | In Roadmap – add BEDE details | — | — | #21: bi-directional – disbursement fund movement, repayment detection, daily reconciliation. | Custom. | Disbursement direction missing (see FR-16); daily recon partial (FR-13). | Add CBS outbound disbursement + recon.
INT-06 | BEDE Scope | Integration | 5 Integrations | Credit bureau (Bahrain Credit Reference Bureau / BENEFIT) – outbound reporting of facilities, delinquencies, closures. | — | — | — | — | Missing from Roadmap | Outside Mifos | Integration layer: periodic BCRB/BENEFIT reporting file/API built from Fineract data (facilities, delinquencies, closures). Fineract only supplies data via API/report. | NEW roadmap item: Credit bureau (Bahrain Credit Reference Bureau / BENEFIT) – outbound reporting of facilities, delinquencies, closures. | Custom. | Not in roadmap. (Optasia comparison only covers inbound bureau checks for decisioning.) | Add task: periodic bureau reporting file/API.
INT-07 | BEDE Scope | Integration | 5 Integrations | AML / sanctions screening – outbound hooks at onboarding and disbursement. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: hold/hook points before client activation and before disbursement (screening status field). Outside: call to AML/sanctions provider through the integration layer. | NEW roadmap item: AML / sanctions screening – outbound hooks at onboarding and disbursement. | Custom. | Not in roadmap. | Add task: screening hooks + hold/release logic.
INT-08 | BEDE Scope | Integration | 5 Integrations | Notification providers (SMS, push, email, WhatsApp). | #16 | #16 Loan Notifications & Reminder Orchestration | #16: 4 | P1 | In Roadmap – add BEDE details | — | — | #16: providers for SMS, push, email, WhatsApp. | Custom. | WhatsApp/email providers not explicit. | Extend #16.
INT-09 | BEDE Scope | Integration | 5 Integrations | Company data warehouse – outbound read replica / CDC feed (FR-35). | — | — | — | — | Missing from Roadmap | Outside Mifos | Same as FR-35 – Bede AWS read replica / CDC to data warehouse. | NEW roadmap item: Company data warehouse – outbound read replica / CDC feed (FR-35). | Not native. | Same gap as FR-35. | See FR-35.
INT-10 | BEDE Scope | Integration | 5 Integrations | Identity provider (SSO) – inbound staff authentication. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Outside: identity provider. Mifos: OIDC/SAML configuration of Fineract and the Mifos web app login. | NEW roadmap item: Identity provider (SSO) – inbound staff authentication. | Configurable (OAuth2/OIDC). | Not in roadmap. | See FR-31.
INT-STD-1 | BEDE Scope | Integration standard | 5 Integration standards | OpenAPI 3.x specs delivered and maintained for every API. | — | — | — | — | Native – no roadmap item needed | — | — | No roadmap item – configure during implementation. | Native OpenAPI for Fineract core APIs. | Custom APIs (facade, Murabaha, integrations) need specs. | Include in definition of done.
INT-STD-2 | BEDE Scope | Integration standard | 5 Integration standards | Idempotent operations, retry with back-off, dead-letter handling and automated reconciliation for every external system. | — | — | — | — | Missing from Roadmap | Outside Mifos | Integration layer / middleware (message broker, retry with back-off, dead-letter queue, reconciliation jobs). Fineract idempotency-key header already native. | NEW roadmap item: Idempotent operations, retry with back-off, dead-letter handling and automated reconciliation for every external system. | Partial: Fineract idempotency-key support; retry/DLQ custom. | Cross-cutting effort not estimated. | Add integration-framework task (retry/DLQ/recon).
INT-STD-3 | BEDE Scope | Integration standard | 5 Integration standards | Event / webhook support for status changes. | — | — | — | — | Native – no roadmap item needed | — | — | No roadmap item – configure during implementation. | Native hooks + external business events (Kafka/ActiveMQ). | Configuration; custom Murabaha events to be added. | Configure.
INT-STD-4 | BEDE Scope | Integration standard | 5 Integration standards | API versioning with documented deprecation policy. | — | — | — | — | Missing from Roadmap | Outside Mifos | API gateway + API governance document (versioning, deprecation policy). | NEW roadmap item: API versioning with documented deprecation policy. | Process / documentation. | Not covered. | Add to API governance deliverables.
INT-STD-5 | BEDE Scope | Integration standard | 5 Integration standards | No customer PII in URLs, query strings or logs. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: review endpoints that pass PII in query strings, log masking config. Outside: API gateway / log pipeline filtering. | NEW roadmap item: No customer PII in URLs, query strings or logs. | Not guaranteed natively (some endpoints use query params, logs not masked). | Review + log masking needed (see NFR-08). | Add security hardening task.
NFR-01 | BEDE Scope | NFR | 6.1 Availability & performance | Availability [99.9%] monthly, excl. agreed maintenance. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Depends on Bede AWS (multi-AZ) + stateless scale-out. | No effort/commitment in task list. | Architecture sizing + SLA commitment in response.
NFR-02 | BEDE Scope | NFR | 6.1 Availability & performance | RTO [1 hour]; RPO [15 minutes]. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Infra (Bede). | FOO provides DR procedure/spec only. | Include DR spec deliverable.
NFR-03 | BEDE Scope | NFR | 6.1 Availability & performance | [X] TPS; API p95 < [500 ms] for customer-facing calls. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Depends on sizing. | TPS figure is still [X] in BEDE doc. | Ask BEDE for volumes; include perf tuning effort.
NFR-04 | BEDE Scope | NFR | 6.1 Availability & performance | Performance test at [3–5x] projected peak before go-live, results delivered. | — | — | — | — | Missing from Roadmap | Outside Mifos | Performance test tooling & execution (e.g. JMeter/k6) against Bede UAT/perf environment. | NEW roadmap item: Performance test at [3–5x] projected peak before go-live, results delivered. | — | No QA/perf-test effort in estimate (estimate = 1 developer). | Add performance testing effort.
NFR-05 | BEDE Scope | NFR | 6.1 Availability & performance | Multi-AZ deployment in AWS Ireland (eu-west-1); DR procedure tested before go-live and annually. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Infra (Bede). | DR test support effort not estimated. | Add DR test support.
NFR-06 | BEDE Scope | NFR | 6.2 Security | All customer data stored and processed in Bede's AWS account. | — | — | — | — | Conflicts with Roadmap item | N/A – architecture | Satisfied by self-hosting Fineract in Bede AWS; issue only with the Mambu option. | — | Fineract self-hosted: OK. | Task list has a "Owner if BEDE Select Mambu" option. Mambu is a vendor-hosted SaaS – data would not sit in Bede's AWS. | If FOO/Fineract route: compliant. Remove or caveat the Mambu columns.
NFR-07 | BEDE Scope | NFR | 6.2 Security | Encryption at rest & in transit (TLS 1.2+); secrets in managed vault, never in code/config. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Outside: AWS KMS, RDS encryption, Secrets Manager, TLS at load balancer. Mifos: Fineract reads secrets from vault/env – configuration only. | NEW roadmap item: Encryption at rest & in transit (TLS 1.2+); secrets in managed vault, never in code/config. | Configurable (KMS / Secrets Manager integration). | Not estimated. | Add DevOps/security task.
NFR-08 | BEDE Scope | NFR | 6.2 Security | Field-level PII masking in technical logs; separate PII log tier for authorised staff only. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: field-level PII masking in Fineract logging (logback pattern/masking converter) for custom and core logs. Outside: separate PII log tier/access in Bede log platform. | NEW roadmap item: Field-level PII masking in technical logs; separate PII log tier for authorised staff only. | Not native. | Not estimated. | Add log-masking task.
NFR-09 | BEDE Scope | NFR | 6.2 Security | SAST, DAST, dependency & container scanning in CI/CD; results shared with Bede. | — | — | — | — | Missing from Roadmap | Outside Mifos | CI/CD pipeline: SAST, DAST, dependency & container scanning; reports shared with Bede. | NEW roadmap item: SAST, DAST, dependency & container scanning in CI/CD; results shared with Bede. | Pipeline work. | Not estimated. | Add DevSecOps effort.
NFR-10 | BEDE Scope | NFR | 6.2 Security | Independent pen test before go-live & annually; critical/high fixed before go-live. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Third-party cost. | Not in estimate or commercials. | Price pen test + remediation buffer.
NFR-11 | BEDE Scope | NFR | 6.2 Security | Vulnerability SLAs: Critical [72h], High [14 days], Medium/Low [30 days]. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Support process. | Commercial/support commitment. | Confirm in support model.
NFR-12 | BEDE Scope | NFR | 6.2 Security | Alignment with OWASP ASVS and CBB cybersecurity requirements. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Not estimated. | Gap assessment vs ASVS.
NFR-13 | BEDE Scope | NFR | 6.2 Security | Foo personnel named, background-checked, individual MFA accounts. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | HR / process. | Non-dev. | Confirm in response.
NFR-14 | BEDE Scope | NFR | 6.3 Observability | Structured logs, metrics, distributed traces and health endpoints for Company monitoring tools. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: enable actuator health/metrics, structured JSON logs, OpenTelemetry tracing (configuration). Outside: Bede monitoring tools ingest them. | NEW roadmap item: Structured logs, metrics, distributed traces and health endpoints for Company monitoring tools. | Native actuator health/metrics; tracing configurable. | Not estimated. | Add observability task (incl. FR-39 job alerting).
NFR-15 | BEDE Scope | NFR | 6.3 Observability | Alert definitions and runbooks for every critical failure mode. | — | — | — | — | Missing from Roadmap | Outside Mifos | Alert definitions in the monitoring stack + runbook documents. | NEW roadmap item: Alert definitions and runbooks for every critical failure mode. | Deliverable. | Not estimated. | Add runbook effort.
NFR-16 | BEDE Scope | NFR | 6.3 Observability | Configurable data retention and purge policies (CBB & PDPL). | — | — | — | — | Missing from Roadmap | Inside Mifos / Fineract | Fineract: configurable retention rules + archival/purge jobs (no native purge) respecting CBB and PDPL periods. | NEW roadmap item: Configurable data retention and purge policies (CBB & PDPL). | Not native. | Not estimated. | Add retention/purge task.
NFR-17 | BEDE Scope | NFR | 6.4 Architecture & deployment | Containerised on Bede EKS; IaC (Terraform/Helm) for instant deployment to recovery regions. | — | — | — | — | Missing from Roadmap | Outside Mifos | DevOps: Helm charts + Terraform for EKS; Fineract Docker images already exist. | NEW roadmap item: Containerised on Bede EKS; IaC (Terraform/Helm) for instant deployment to recovery regions. | Docker images native; Helm/Terraform to build. | Conflicts with Mambu option (SaaS, not deployable to EKS). | Add Helm/Terraform packaging task.
NFR-18 | BEDE Scope | NFR | 6.4 Architecture & deployment | Environment parity across dev, UAT and production. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Process. | Non-dev. | Covered by IaC.
NFR-19 | BEDE Scope | NFR | 6.4 Architecture & deployment | Built on Apache Fineract or similar open-source platform; upstream version pinned, documented upgrade path, no fork off upstream. | — | — | — | — | Conflicts with Roadmap item | N/A – architecture | Deliver FOO customisations as Fineract extension modules on a pinned upstream version (no fork). | — | FOO CBS is Fineract-based: aligned in principle. | (1) Mambu option = proprietary, does not meet this. (2) FOO customisations (Murabaha etc.) must be delivered as modules/extensions, not as a fork. | Confirm delivery as extension modules; drop Mambu columns for this scope.
NFR-20 | BEDE Scope | NFR | 6.4 Architecture & deployment | Zero-downtime deployments by default; any interruption justified and approved in advance. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: backward-compatible Liquibase migrations (expand/contract). Outside: Kubernetes rolling / blue-green deployment. | NEW roadmap item: Zero-downtime deployments by default; any interruption justified and approved in advance. | Risk: Liquibase DB migrations may need downtime. | Not estimated. | Rolling-deploy + backward-compatible migration approach.
NFR-21 | BEDE Scope | NFR | 6.4 Architecture & deployment | Every deployment supports straightforward, tested rollback. | — | — | — | — | Missing from Roadmap | Split – Mifos + outside | Mifos: reversible DB changesets / migration strategy. Outside: Helm rollback + tested rollback procedure. | NEW roadmap item: Every deployment supports straightforward, tested rollback. | Risk: DB migrations are not always reversible. | Not estimated. | Define rollback strategy per release.
D-01 | BEDE Scope | Delivery | 7.1 Discovery | Foo team/expert on site for specification workshops. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Discovery/on-site effort not in estimate. | Add discovery phase effort + travel.
D-02 | BEDE Scope | Delivery | 7.1 Discovery | Deliverables: BRD, functional spec, solution architecture, integration specs, data model, signed-off backlog with acceptance criteria. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Not estimated. | Add BA/architect effort.
D-03 | BEDE Scope | Delivery | 7.2 Environments | Bede provisions and manages all AWS environments. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Dependency on Bede. | Record as assumption.
D-04 | BEDE Scope | Delivery | 7.2 Environments | Foo deployment access to development environment only. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Constraint. | Record as assumption.
D-05 | BEDE Scope | Delivery | 7.2 Environments | Bede deploys UAT/prod using Foo-supplied tested packages & step-by-step guides. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Packaging + deployment guides not estimated. | Add DevOps effort.
D-06 | BEDE Scope | Delivery | 7.2 Environments | Foo gets PII-masked logs only (NFR-08). | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Depends on NFR-08. | —
D-07 | BEDE Scope | Delivery | 7.3 Testing | DoD and acceptance criteria agreed per feature before build. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | Process. | — | Plan.
D-08 | BEDE Scope | Delivery | 7.3 Testing | Foo delivers unit, integration and SIT with evidence; UAT test cases and anonymised test data. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | No QA effort in estimate ("1 developer"). | Add QA/SIT effort (typically 25–35% of dev).
D-09 | BEDE Scope | Delivery | 7.3 Testing | Bede UAT with written sign-off; no Sev1/Sev2 open at go-live. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | UAT support effort not estimated. | Add UAT support.
D-10 | BEDE Scope | Delivery | 7.3 Testing | Performance, pen-test and DR tests are acceptance gates. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | See NFR-04/05/10. | —
D-11 | BEDE Scope | Delivery | 7.4 Documentation | Admin guide, ops runbooks, API docs, deployment & rollback guides, architecture & data model docs. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Not estimated. | Add documentation effort.
D-12 | BEDE Scope | Delivery | 7.4 Training | Training for ops, finance, risk, compliance, IT; recordings retained by Bede. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Not estimated. | Add training effort.
M-01 | BEDE Scope | Migration | 8 Migration | Migrate all existing customers, contracts, schedules, repayment history, balances and documents. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: customers, contracts, schedules, repayment history, balances AND documents. | Fineract import/APIs. | #36 = 10 MD; likely low given M-02..M-08. | Re-estimate #36 including all M items.
M-02 | BEDE Scope | Migration | 8 Migration | Field-level data mapping document agreed before first simulation. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: field-level mapping document agreed with BEDE before first simulation. | — | Not explicit in #36. | Include in #36.
M-03 | BEDE Scope | Migration | 8 Migration | Reconciliation to the fils on all balances & schedules; report + sign-off as go-live gate. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: reconciliation to the fils on all balances & schedules; reconciliation report; BEDE sign-off = go-live gate. | — | Not explicit. | Include reconciliation tooling.
M-04 | BEDE Scope | Migration | 8 Migration | Historical repayment history and original contract terms preserved and visible. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: historical repayment history and original contract terms preserved and visible. | Backdated transaction replay needed. | Effort driver not visible in #36. | Include history replay.
M-05 | BEDE Scope | Migration | 8 Migration | Multiple full simulation cycles using a new app build connected to new LMS, without interrupting existing app. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: multiple full simulation cycles with a new app build on the new LMS, without interrupting the live app/backend. | — | Number of cycles not defined. | Agree cycle count (e.g. 3) and estimate.
M-06 | BEDE Scope | Migration | 8 Migration | Production cut-over downtime ≤ [2 hours]. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: production cut-over downtime ≤ [2 hours]. | — | Needs rehearsal & tooling. | Include.
M-07 | BEDE Scope | Migration | 8 Migration | Documented & rehearsed rollback plan for cut-over. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: documented and rehearsed cut-over rollback plan. | — | Not explicit. | Include.
M-08 | BEDE Scope | Migration | 8 Migration | Data freeze window, communication plan, post-migration validation checklist. | #36 | #36 Data Migration | #36: 10 | P1 | In Roadmap – add BEDE details | — | — | #36: data-freeze window, communication plan, post-migration validation checklist. | — | Not explicit. | Include.
S-01 | BEDE Scope | Support | 9 Hypercare | Hypercare 3–6 months post go-live with on-ground presence and daily review calls. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Not in roadmap / estimate. | Price hypercare.
S-02 | BEDE Scope | Support | 9 Warranty | Warranty 5 years post go-live; all defects corrected at no cost. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | 5-year free defect correction is a significant commercial risk. | Commercial review.
S-03 | BEDE Scope | Support | 9 Support | 24x7 support by phone/email/portal, escalation to executive level, English & Arabic. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Not in roadmap / estimate. | Price support model.
S-04 | BEDE Scope | Support | 9 SLAs | Sev1 15 min response / 2 h resolution; Sev2 30 min / 8 h; Sev3 4 h / 3 days; Sev4 1 day / next release. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Aggressive Sev1/Sev2 targets. | Validate feasibility / propose SLA.
S-05 | BEDE Scope | Support | 9 Monthly items | Monthly security & hotfix release with vulnerability/bug report. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Requires tracking upstream Fineract CVEs (ties to NFR-19). | Price recurring effort.
S-06 | BEDE Scope | Support | 9 Monthly items | Monthly service review (SLA, incidents, RCA, capacity, changes). | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Price.
S-07 | BEDE Scope | Support | 9 Monthly items | Service credits / penalties for SLA breaches (§10). | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | See C-03. | Commercial review.
C-01 | BEDE Scope | Commercial | 10 Commercial terms | IP: Bede owns all custom code, configuration, documentation and data; source in Bede repo or escrow. | — | — | — | — | Conflicts with Roadmap item | N/A – commercial | Contract/IP clause – no build. | — | — | Murabaha / Islamic modules are FOO product IP reused across clients – full Bede ownership of "all custom code" conflicts with that. | Commercial/legal review: licence FOO modules, assign only Bede-specific code.
C-02 | BEDE Scope | Commercial | 10 Commercial terms | Milestone payments tied to acceptance; 20% retention released 3 months post go-live. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Commercial review.
C-03 | BEDE Scope | Commercial | 10 Commercial terms | Service credits 5% of monthly fee per breach, capped 20%/month; repeated breaches = termination. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Commercial review.
C-04 | BEDE Scope | Commercial | 10 Commercial terms | Liquidated damages: 8% of contract value per week of delay. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | High LD rate with no cap stated. | Commercial review – negotiate cap.
C-05 | BEDE Scope | Commercial | 10 Commercial terms | Change control with impact assessment; rate card agreed at signature. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Provide rate card.
C-06 | BEDE Scope | Commercial | 10 Commercial terms | Named key personnel; no subcontracting without consent. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Confirm team.
C-07 | BEDE Scope | Commercial | 10 Commercial terms | CBB outsourcing obligations: audit rights, CBB access to Foo premises/staff/records, data location, notification of changes. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Compliance review.
C-08 | BEDE Scope | Commercial | 10 Commercial terms | Foo business continuity plan maintained and tested. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Provide BCP.
C-09 | BEDE Scope | Commercial | 10 Commercial terms | Exit: 6 months transition assistance, return of data & code, destruction certificates. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Price exit support.
C-10 | BEDE Scope | Commercial | 10 Commercial terms | NDA + DPA aligned to Bahrain PDPL. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Legal.
C-11 | BEDE Scope | Commercial | 10 Commercial terms | Liability cap, indemnities (incl. IP), PI / cyber insurance at [amount]. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | Amount TBD. | Legal.
C-12 | BEDE Scope | Commercial | 10 Commercial terms | Term: 5 years support & maintenance, annual renewal, pricing review. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Commercial.
G-01 | BEDE Scope | Governance | 10 Governance | Monthly steering committee. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | PM/governance effort not in estimate. | Add PM effort.
G-02 | BEDE Scope | Governance | 10 Governance | Weekly status report & meeting; shared RAID log. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Add PM effort.
G-03 | BEDE Scope | Governance | 10 Governance | Single Foo PM as point of accountability. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Assign PM.
G-04 | BEDE Scope | Governance | 10 Governance | All decisions, scope changes, acceptances in writing. | — | — | — | — | Non-roadmap (delivery / support / commercial) | — | — | — | — | — | Process.
ROADMAP ITEMS WITH NO / CONFLICTING BEDE REQUIREMENT (not needed for BEDE, or to be reshaped)
RM-2 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #2 | #2 Configurable RAC / Hard Eligibility Rules | 3 | P1 | Roadmap only – not required by BEDE | — | — | — | — | Eligibility Engine is in-house and OUT of scope (§3.2). RAC/hard rules belong to BEDE's engine. | Exclude from BEDE estimate (engine is BEDE in-house, §3.2); keep in product roadmap.
RM-4 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #4 | #4 Credit Scoring Input Attributes & Data Mapping | not estimated | P1 | Roadmap only – not required by BEDE | — | — | — | — | Scoring attributes/data mapping is engine work (§3.2 out of scope). Not estimated anyway. | Exclude from BEDE estimate; keep in product roadmap.
RM-5 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #5 | #5 LMS–Credit Scoring Platform Integration | 2 | P1 | Roadmap only – not required by BEDE | — | — | — | — | No credit-scoring platform integration in BEDE integration list (INT-01..10). | Exclude from BEDE estimate unless INT-02 is resolved as FOO scoring.
RM-7 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #7 | #7 Persist decisioning snapshot for audit and care portal | 1.5 | P1 | Roadmap – rescope to BEDE wording | — | — | — | — | Decision snapshot not required; BEDE needs immutable audit (FR-33) and engine output stored with application. | Rescope to "store Eligibility Engine output with application".
RM-9 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #9 | #9 Enforce one active loan per customer | 1 | P1 | Conflicts with Roadmap item | Inside Mifos / Fineract | Fineract: change to exposure limits (see FR-21). | — | — | Contradicts FR-21 (multiple concurrent finances). | Replace with exposure-limit task.
RM-10.4 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #10.4 | #10.4 Takaful / Insurance Classification & Treatment | 3 | P1 | Roadmap only – not required by BEDE | — | — | — | — | Takaful/insurance not mentioned anywhere in BEDE scope. | Exclude from BEDE estimate unless BEDE confirms Takaful (−3 MD).
RM-10.6 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #10.6 | #10.6 Murabaha Accounting, GL, Profit Suspension & Odoo Integration | 18 | P1 | Roadmap – rescope to BEDE wording | — | — | — | — | Odoo/ERP integration not in BEDE scope; BEDE asks for LMS sub-ledger + CBS reconciliation (FR-11, FR-13). | Remove Odoo part; keep GL/profit suspension.
RM-11.2 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #11.2 | #11.2 Multi-Currency Purchase & FX | 7 | P1 | Roadmap only – not required by BEDE | — | — | — | — | Multi-currency purchase & FX not requested (BHD Murabaha via app). | Exclude from BEDE estimate unless BEDE confirms FX (−7 MD).
RM-11.4 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #11.4 | #11.4 Wakala Workflow | 7 | P1 | Roadmap only – not required by BEDE | — | — | — | — | Wakala is a different Islamic contract; BEDE scope is Murabaha only. | Exclude from BEDE estimate (−7 MD); keep in product roadmap.
RM-11.6 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #11.6 | #11.6 Wa'd & Hamish Jiddiyyah | 5 | P1 | Roadmap – rescope to BEDE wording | — | — | — | — | Wa'd / Hamish Jiddiyyah not explicitly requested; may be needed by SSB for commodity Murabaha. | Confirm with BEDE SSB before keeping (5 MD).
RM-18 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #18 | #18 Loan Offer Caching & Refresh | 3.5 | P2 | Roadmap only – not required by BEDE | — | — | — | — | Offer caching is Optasia-specific; not in BEDE requirements. | Exclude from BEDE estimate (−3.5 MD).
RM-19 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #19 | #19 Application Expiry & Automatic Cancellation | 2 | P2 | Roadmap only – not required by BEDE | — | — | — | — | 72h application expiry is Optasia-specific; not in BEDE requirements. | Exclude from BEDE estimate unless confirmed (−2 MD).
RM-20 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #20 | #20 Promo Code & Promotional Discount Support | 2 | P2 | Roadmap only – not required by BEDE | — | — | — | — | Promo codes not in BEDE requirements. | Exclude from BEDE estimate (−2 MD).
RM-22 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #22 | #22 Accounting / ERP Integration | 5 | P2 | Roadmap only – not required by BEDE | — | — | — | — | No ERP integration in BEDE integration list. | Exclude from BEDE estimate unless confirmed (−5 MD).
RM-23 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #23 | #23 CRM / Ticketing Integration | 2 | P2 | Roadmap only – not required by BEDE | — | — | — | — | CRM/ticketing not in BEDE integration list. | Exclude from BEDE estimate (−2 MD).
RM-24 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #24 | #24 Borrower Data Refresh / Re-registration | 2 | P2 | Roadmap only – not required by BEDE | — | — | — | — | Borrower re-registration is Optasia-specific. | Exclude from BEDE estimate (−2 MD).
RM-25 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #25 | #25 Regulatory APR Calculation | 0 | P2 | Roadmap – keep (implied by CBB) | — | — | — | — | APR not explicit in BEDE doc but implied by CBB Rulebook Vol.5 consumer disclosure (Bede is CBB-licensed). | Keep with #10.7; currently 0 MD – estimate it.
RM-10.7 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #10.7 | #10.7 CBB Consumer Disclosure | 3 | P1 | Roadmap – keep (implied by CBB) | — | — | — | — | CBB consumer disclosure not explicit but implied by CBB licence. | Keep.
RM-27 | Roadmap only | Roadmap | — | — (no explicit BEDE requirement) | #27 | #27 EMI schedule, oldest-unpaid-first allocation, partial repayment held until full EMI | 2.5 | P2 | Conflicts with Roadmap item | Inside Mifos / Fineract | Fineract: change allocation (see FR-19). | — | — | "Partial repayment held until full EMI" contradicts FR-19. | Rework (see FR-19).
RM-MAMBU | Roadmap only | Roadmap | — | — (no BEDE requirement) | Cols K/L | Owner / Estimation if BEDE selects Mambu | — | — | Conflicts with Roadmap item | N/A – architecture | Option conflicts with NFR-06/17/19. | — | — | Columns K/L "Owner / Estimation if BEDE select Mambu": Mambu is proprietary SaaS – conflicts with NFR-19 (open-source, no fork), NFR-06 (data in Bede AWS) and NFR-17 (deploy to Bede EKS). | Drop the Mambu option for this response, or flag it as non-compliant.

## BEDE Coverage by FRD
BEDE Requirements – FRD Coverage and LMS Side
All requirements listed in the BEDE Scope & Requirements document and their coverage by the current FOO documents. Delivery, support, commercial and governance items (D-, S-, C-, G-) are marked 'Non-product feature'.
Documents |  |  |  | Coverage status | Count | of which LMS side = Yes |  | LMS side | Count
Islamic Financing Module FRD | Islamic Financing Module for Loan Management System (LMS) – v4 |  |  | Covered | 6 | 6 |  | Yes | 23
Murabaha Profit FRD | Murabaha Profit Configuration, Contractual Profit Controls & Rescheduling – FRD v14 |  |  | Partly covered | 26 | 12 |  | Partly | 37
Ibra' BRD | Murabaha Early Settlement & Ibra' Management – BRD v7 |  |  | Native – no FRD needed | 1 | 1 |  | No | 58
Mid-term Grace FRD | Mid-term Grace Period Enhancement for LMS – v3 |  |  | Not covered | 50 | 4 |  | Total | 118
Native | Existing Fineract / FOO LMS capability, used through configuration |  |  | Non-product feature | 35 | 0
|  |  |  | Total | 118 | 23 |  | Yes = built in the LMS · Partly = LMS + external system · No = outside the LMS
Ref ID | Category | BEDE Section | BEDE Requirement | Coverage Status | Covered in (document & section) | LMS Side? | Outside-LMS Part | Still Missing / Next Step | Roadmap Item #
FR-01 | Functional | 4.1 Product configuration | Fully configurable Sharia-compliant financing products with no code changes: term, min/max amount, profit rate, fees, repayment frequency, grace periods, eligibility tags. | Partly covered | Islamic Financing Module FRD §2–3 (Islamic product, Financing Type); Murabaha Profit FRD §3–4 (Profit Input Type, Profit Amount min/default/max); Mid-term Grace FRD §3 (grace limits per product); Native: term, amount, fees, frequency | Yes | — | Eligibility tags on the product | #29, #10.1, #11.7
FR-02 | Functional | 4.1 Product configuration | Product variants driven by type of good financed, customer nationality, credit report outcome, and any other attribute exposed by the Eligibility Engine. | Not covered | — | Partly | Eligibility Engine rules | Product variants by type of good, nationality, credit outcome (roadmap #6) | #6
FR-03 | Functional | 4.1 Product configuration | Customisable, reusable repayment schedule templates incl. irregular patterns (pay one month, skip two), bullet, step-up/step-down, seasonal. | Partly covered | Murabaha Profit FRD §5.6 (variable instalments keep totals); Native: frequencies, variable instalments | Yes | — | Reusable schedule templates; skip / seasonal / step-down patterns (roadmap #11.7) | #11.7
FR-04 | Functional | 4.1 Product configuration | Configurable repayment allocation order (fees/profit/principal), day-count convention, rounding rules, weekend & public-holiday handling. | Covered | Native configuration; Islamic Financing Module FRD §9.2 (payment allocation); Murabaha Profit FRD §5.3, §6.15 (rounding, holiday shifts never change Profit) | Yes | — | — | #27, #29
FR-05 | Functional | 4.1 Product configuration | Product versioning: changes apply to new contracts only unless explicitly migrated; full history retained. | Not covered | — | Yes | — | Product versioning (new FRD) | —
FR-06 | Functional | 4.1 Product configuration | Sharia Supervisory Board approval recorded against each product version as an acceptance gate before activation. | Not covered | — | Yes | — | Sharia Supervisory Board approval gate per product version (new FRD) | —
FR-07 | Functional | 4.2 Murabaha mechanics | Explicit Murabaha contract model: cost price, profit amount, total sale price; commodity purchase then sale to customer. | Partly covered | Islamic Financing Module FRD §5, §7, §8, §12 (commodity reference, Cost Price, Selling Price); Murabaha Profit FRD §4–5 (Fixed Profit Amount, Selling Price fixed) | Partly | Murabaha workflow system, commodity platform | Commodity purchase & sale execution steps (roadmap #11.5 / external workflow) | #10.1, #10.2, #11.5
FR-08 | Functional | 4.2 Murabaha mechanics | Murabaha sale contract & offer/acceptance documents in Arabic and English, presented and e-signed in the app before disbursement, stored with the loan record. | Not covered | — | Partly | Document generation & e-sign in the app | Contract & offer/acceptance documents AR/EN, e-sign, stored with the financing (roadmap #11.1, #10.7) | #11.1, #10.7
FR-09 | Functional | 4.2 Murabaha mechanics | Profit recognition rules configurable per product; no compounding of profit; late payment charges routed to a designated charity account, not income. | Partly covered | Murabaha Profit FRD §6.3, §6.12, §6.16 (no compounding; late charges kept separate from Profit) | Yes | — | Late charges to charity account; profit recognition rules per product (roadmap #10.5, #10.6) | #10.5, #10.6
FR-10 | Functional | 4.2 Murabaha mechanics | Profit rebate (ibra') rules configurable per product for early AND partial settlement. | Covered | Ibra' BRD BR-2 (Ibra' methods per product), BR-5 (partial early settlement) | Yes | — | — | #10.3, #15
FR-11 | Functional | 4.2 Murabaha mechanics | Full accounting sub-ledger: chart of accounts, automated journal postings for every financial event, month-end & year-end close, audit-ready trial balance. | Partly covered | Islamic Financing Module FRD §13 (existing accounting engine reused); Murabaha Profit FRD §6.16, §8.8; Native: GL, journal entries, closures | Yes | — | Murabaha GL model and postings (roadmap #10.6) | #10.6
FR-12 | Functional | 4.2 Murabaha mechanics | IFRS 9 / AAOIFI staging & provisioning outputs (DPD, stage classification, ECL inputs) per loan and portfolio. | Not covered | — | Partly | ECL model / provisioning engine | IFRS 9 / AAOIFI staging & ECL inputs; "under deferment" flag (roadmap #11.3, #31) | #11.3, #31
FR-13 | Functional | 4.2 Murabaha mechanics | Daily automated reconciliation of the LMS sub-ledger against the Core Banking System with exception reporting. | Not covered | — | Partly | Core Banking System | Daily LMS vs CBS reconciliation with exceptions (roadmap #21) | #21
FR-14 | Functional | 4.3 Loan lifecycle | Application from the app; LMS receives eligibility output and returns eligible products, terms and indicative schedules. | Partly covered | Islamic Financing Module FRD §11.2, §11.4 (creation & schedule APIs); Murabaha Profit FRD §8.7 (schedule calculation with profitAmount) | Partly | Mobile app, Eligibility Engine | Eligible products from Eligibility Engine output (roadmap #3, #6, #17) | #3, #6, #17
FR-15 | Functional | 4.3 Loan lifecycle | Approval workflow with configurable stages, maker-checker, and automated approval where rules permit. | Partly covered | Native maker-checker; Islamic Financing Module FRD §14 | Partly | Murabaha workflow system | Configurable approval stages; rule-based automatic approval (roadmap #17) | #17
FR-16 | Functional | 4.3 Loan lifecycle | Disbursement to customer account or merchant/commodity counterparty, status tracked against Core Banking confirmation. | Not covered | — | Partly | Core Banking System | Disbursement to customer / merchant / commodity counterparty with CBS confirmation (roadmap #11.5) | #11.5
FR-17 | Functional | 4.3 Loan lifecycle | Repayment via the app through integrated payment gateways; repayments received through Core Banking also matched and applied. | Partly covered | Islamic Financing Module FRD §9, §11.5 (repayment processing & API) | Partly | Payment gateways, Core Banking System | Payment-gateway integration and CBS repayment matching (roadmap #21, #27) | #21, #27
FR-18 | Functional | 4.3 Loan lifecycle | Early settlement configurable per product: without profit, with profit, fixed fee, or % of settled amount. Settlement quote generated in-app. | Covered | Ibra' BRD BR-1/BR-2 (settlement methods), BR-3 (auto-approval), BR-6 (in-app quote API); Murabaha Profit FRD §6.13, §6.21 (payoff) | Yes | Quote screen in the app | Dependency: Early Settlement charge for fixed fee / % options (roadmap #12, #13) | #12, #13, #14, #15, #10.3
FR-19 | Functional | 4.3 Loan lifecycle | Partial payment with the same charging options as FR-18 and automatic schedule recalculation. | Covered | Ibra' BRD BR-5 (partial early settlement with Ibra', arrears first, last instalments); Murabaha Profit FRD §6.5, §6.11 (Profit unchanged) | Yes | — | — | #27
FR-20 | Functional | 4.3 Loan lifecycle | Loan top-up with configurable eligibility, re-underwriting via Eligibility Engine, treated as new or consolidated contract per product. | Partly covered | Murabaha Profit FRD §8.1, §6.21 (native top-up blocked for Murabaha) | Partly | Eligibility Engine re-underwriting | Sharia-compliant top-up flow, new vs consolidated contract (new FRD) | —
FR-21 | Functional | 4.3 Loan lifecycle | Multiple concurrent finances per customer, with portfolio-level exposure limits configurable per product and customer segment. | Not covered | Native: multiple loans per client | Yes | — | Exposure limits per product & customer segment (conflicts with roadmap #9) | #9
FR-22 | Functional | 4.3 Loan lifecycle | Deferment for a configurable number of days/months, with limits per product and configurable treatment of profit during deferment. | Partly covered | Mid-term Grace FRD §3–4 (grace limits per product, maker-checker); Murabaha Profit FRD §6.6–6.8 (deferment never changes Profit) | Yes | — | Deferment in days (product limit); Murabaha cross-reference in the Grace FRD; deferment API for the app | #11.7, #10.1
FR-23 | Functional | 4.3 Loan lifecycle | Restructuring and rescheduling (staff-initiated) with maker-checker approval and full audit trail. | Covered | Murabaha Profit FRD §6, §8.4–8.6; Mid-term Grace FRD §4.4; Native reschedule + maker-checker | Yes | — | — | #10.1
FR-24 | Functional | 4.3 Loan lifecycle | Write-off, fee waiver, refund and overpayment handling with maker-checker approval. | Partly covered | Murabaha Profit FRD §6.14, §6.19, §6.20 (reversal, Waive Interest blocked, write-off); Ibra' BRD BR-1 (profit waiver only via Ibra'); Native: fee waiver, refund, overpayment | Yes | — | Partial write-off to verify (roadmap #28) | #28, #14
FR-25 | Functional | 4.3 Loan lifecycle | Customer statements, repayment schedules and settlement quotes on demand from the app and the back-office console. | Partly covered | Ibra' BRD BR-6 (settlement quote API); Islamic Financing Module FRD §11.4 (schedule API); Murabaha Profit FRD §6.21 | Partly | Statement / schedule screens in the app | Customer statements (app and back-office) | —
FR-26 | Functional | 4.4 Collections & defaults | Default & delinquency rules configurable per product (DPD thresholds, amount thresholds, missed instalment count). | Partly covered | Native DPD buckets; Murabaha Profit FRD §6.12 (delinquency never adds Profit) | Yes | — | Amount and missed-instalment thresholds (roadmap #26, #35) | #26, #35
FR-27 | Functional | 4.4 Collections & defaults | Delinquency staging (pre-due reminder, 1–30, 31–60, 61–90, 90+, legal) with configurable names, thresholds and actions. | Partly covered | Native delinquency buckets; Murabaha Profit FRD §6.12 | Partly | Collections / notification actions | Pre-due and legal stages with configurable actions (roadmap #16, #35) | #16, #35
FR-28 | Functional | 4.4 Collections & defaults | Automated notifications to customers and internal teams, templates configurable per product, per stage, per channel. | Not covered | — | Partly | Notification hub | Notification templates per product, stage and channel (roadmap #16) | #16
FR-29 | Functional | 4.4 Collections & defaults | Channels: SMS, push, email, WhatsApp; Arabic & English; delivery status tracked. | Not covered | — | Partly | Notification providers | SMS, push, email, WhatsApp; AR/EN; delivery status (roadmap #16) | #16
FR-30 | Functional | 4.4 Collections & defaults | Collections work queues in back-office console, promise-to-pay tracking and contact history. | Not covered | — | No | Collections tool / back-office console | Collections work queues, promise-to-pay, contact history | —
FR-31 | Functional | 4.5 Back-office console | Role-based access control with SSO (SAML/OIDC) and MFA; segregation of duties enforced. | Partly covered | Native RBAC & maker-checker; Islamic Financing Module FRD §14 | Partly | Identity provider | SSO (SAML/OIDC) and MFA | —
FR-32 | Functional | 4.5 Back-office console | Maker-checker on all configuration changes and financial adjustments. | Covered | Native; Islamic Financing Module FRD §14; Murabaha Profit FRD §8.5; Ibra' BRD BR-3; Mid-term Grace FRD §4.4 | Yes | — | — | #29
FR-33 | Functional | 4.5 Back-office console | Immutable audit trail of every configuration change, data change and user action, exportable for Internal Audit and CBB. | Partly covered | Islamic Financing Module FRD §15; Murabaha Profit FRD §8.6; Ibra' BRD BR-4; Mid-term Grace FRD §4.4; Native command audit | Yes | — | Export for Internal Audit / CBB; read-action logging (roadmap #7) | #7
FR-34 | Functional | 4.5 Back-office console | Customer 360: profile, contracts, schedules, payments, communications, documents. | Partly covered | Native client view; Islamic Financing Module FRD §7–8 (financing details) | Partly | Notification / document stores | Communications and documents in one Customer 360 view (roadmap #7) | #7
FR-35 | Functional | 4.6 Reporting & data | Analytics access to structured loan data with zero impact on transactional system via read replica or CDC feed to Bede DWH. | Not covered | — | No | Infrastructure / DWH | Read replica / CDC feed to Bede DWH | —
FR-36 | Functional | 4.6 Reporting & data | Full data model documentation: ERD and data dictionary, maintained across releases. | Not covered | — | No | Documentation deliverable | ERD and data dictionary maintained per release | —
FR-37 | Functional | 4.6 Reporting & data | Structured extracts to support CBB regulatory returns and Sharia audit. | Not covered | — | Partly | Regulatory reporting tool | Extracts for CBB returns and Sharia audit (roadmap #34, #31) | #34, #31
FR-38 | Functional | 4.6 Reporting & data | Operational reports: portfolio, disbursements, collections, delinquency aging, settlements, profit recognised. | Partly covered | Islamic Financing Module FRD §16 (existing reports with Islamic terminology); Murabaha Profit FRD §8.8 | Yes | — | Settlement, profit-recognised and aging reports (roadmap #30, #32, #33, #35) | #30, #32, #33, #35
FR-39 | Functional | 4.7 Batch processing | EOD & periodic jobs (accruals, aging, provisioning, dunning, schedule generation) monitored, idempotent, re-runnable, alerting on failure. | Partly covered | Native Fineract scheduler jobs (accruals, aging) | Partly | Monitoring / alerting stack | Monitoring, idempotency and failure alerting for jobs | —
INT-01 | Integration | 5 Integrations | Mobile application & existing mobile backend (built by Foo) – bi-directional, all customer journeys in §4.3. | Partly covered | Islamic Financing Module FRD §11 (product, creation, details, schedule, repayment, terminology APIs); Ibra' BRD BR-6; Murabaha Profit FRD §8.7 | Partly | Mobile app & mobile backend | APIs for deferment, top-up, statements, e-sign journeys | #1
INT-02 | Integration | 5 Integrations | Eligibility Engine (in-house) – inbound to LMS. Direction TBD: engine sends outcome & LMS returns products, OR LMS returns all products & engine filters. | Not covered | — | Partly | Eligibility Engine | Eligibility Engine integration (roadmap #3, #6) | #3, #6
INT-03 | Integration | 5 Integrations | Commodity platform – bi-directional; purchase & sale confirmation for Sharia compliance. | Partly covered | Islamic Financing Module FRD §11.7, §12 (commodity lookup & validation) | Partly | Commodity platform | Purchase and sale confirmation (roadmap #11.5) | #11.5
INT-04 | Integration | 5 Integrations | Payment gateways – inbound; repayment status, reconciliation, refunds. | Not covered | — | Partly | Payment gateways | Payment-gateway status, reconciliation, refunds (roadmap #21) | #21
INT-05 | Integration | 5 Integrations | Core Banking System – bi-directional; disbursement fund movement, repayment detection, daily reconciliation. | Not covered | — | Partly | Core Banking System | CBS disbursement, repayment detection, daily reconciliation (roadmap #21) | #21
INT-06 | Integration | 5 Integrations | Credit bureau (Bahrain Credit Reference Bureau / BENEFIT) – outbound reporting of facilities, delinquencies, closures. | Not covered | — | No | Credit bureau connector | Credit bureau reporting | —
INT-07 | Integration | 5 Integrations | AML / sanctions screening – outbound hooks at onboarding and disbursement. | Not covered | — | Partly | AML / screening system | AML / sanctions hooks at onboarding & disbursement | —
INT-08 | Integration | 5 Integrations | Notification providers (SMS, push, email, WhatsApp). | Not covered | — | No | Notification providers | Notification provider integration (roadmap #16) | #16
INT-09 | Integration | 5 Integrations | Company data warehouse – outbound read replica / CDC feed (FR-35). | Not covered | — | No | Infrastructure / DWH | DWH feed (FR-35) | —
INT-10 | Integration | 5 Integrations | Identity provider (SSO) – inbound staff authentication. | Not covered | — | Partly | Identity provider | SSO identity provider | —
INT-STD-1 | Integration standard | 5 Integration standards | OpenAPI 3.x specs delivered and maintained for every API. | Partly covered | Islamic Financing Module FRD §11; Murabaha Profit FRD §8.7 (API changes specified); Native Swagger/OpenAPI | Yes | — | Published OpenAPI 3.x spec for every new API | —
INT-STD-2 | Integration standard | 5 Integration standards | Idempotent operations, retry with back-off, dead-letter handling and automated reconciliation for every external system. | Partly covered | Islamic Financing Module FRD §11.8 (idempotency), §11.9 (retry & failure handling) | Partly | Integration layer | Dead-letter handling; automated reconciliation per external system | —
INT-STD-3 | Integration standard | 5 Integration standards | Event / webhook support for status changes. | Native – no FRD needed | Native Fineract hooks / external events | Yes | — | Confirm events needed by Bede | —
INT-STD-4 | Integration standard | 5 Integration standards | API versioning with documented deprecation policy. | Partly covered | Islamic Financing Module FRD §11.12 (backward compatibility, existing versioning policy) | Partly | API governance | Documented deprecation policy | —
INT-STD-5 | Integration standard | 5 Integration standards | No customer PII in URLs, query strings or logs. | Not covered | — | Partly | Logging / API gateway | No PII in URLs, query strings or logs | —
NFR-01 | NFR | 6.1 Availability & performance | Availability [99.9%] monthly, excl. agreed maintenance. | Not covered | — | No | Hosting / infrastructure | Availability target | —
NFR-02 | NFR | 6.1 Availability & performance | RTO [1 hour]; RPO [15 minutes]. | Not covered | — | No | Hosting / infrastructure | RTO / RPO | —
NFR-03 | NFR | 6.1 Availability & performance | [X] TPS; API p95 < [500 ms] for customer-facing calls. | Not covered | — | Partly | Infrastructure sizing | Throughput and latency targets | —
NFR-04 | NFR | 6.1 Availability & performance | Performance test at [3–5x] projected peak before go-live, results delivered. | Not covered | — | No | Delivery / testing | Performance test at 3–5x peak | —
NFR-05 | NFR | 6.1 Availability & performance | Multi-AZ deployment in AWS Ireland (eu-west-1); DR procedure tested before go-live and annually. | Not covered | — | No | Hosting / infrastructure | Multi-AZ AWS deployment; DR tests | —
NFR-06 | NFR | 6.2 Security | All customer data stored and processed in Bede's AWS account. | Not covered | — | No | Hosting / infrastructure | Data in Bede's AWS account | —
NFR-07 | NFR | 6.2 Security | Encryption at rest & in transit (TLS 1.2+); secrets in managed vault, never in code/config. | Not covered | — | Partly | Infrastructure | Encryption at rest / in transit; secrets vault | —
NFR-08 | NFR | 6.2 Security | Field-level PII masking in technical logs; separate PII log tier for authorised staff only. | Not covered | — | Partly | Logging stack | PII masking in logs; separate PII log tier | —
NFR-09 | NFR | 6.2 Security | SAST, DAST, dependency & container scanning in CI/CD; results shared with Bede. | Not covered | — | No | CI/CD | SAST / DAST / dependency & container scanning | —
NFR-10 | NFR | 6.2 Security | Independent pen test before go-live & annually; critical/high fixed before go-live. | Not covered | — | No | Delivery | Independent pen test | —
NFR-11 | NFR | 6.2 Security | Vulnerability SLAs: Critical [72h], High [14 days], Medium/Low [30 days]. | Not covered | — | No | Support process | Vulnerability SLAs | —
NFR-12 | NFR | 6.2 Security | Alignment with OWASP ASVS and CBB cybersecurity requirements. | Not covered | — | Partly | Security programme | OWASP ASVS / CBB cybersecurity alignment | —
NFR-13 | NFR | 6.2 Security | Foo personnel named, background-checked, individual MFA accounts. | Not covered | — | No | HR / access process | Named, background-checked personnel with MFA | —
NFR-14 | NFR | 6.3 Observability | Structured logs, metrics, distributed traces and health endpoints for Company monitoring tools. | Not covered | — | Partly | Observability stack | Structured logs, metrics, traces, health endpoints | —
NFR-15 | NFR | 6.3 Observability | Alert definitions and runbooks for every critical failure mode. | Not covered | — | No | Operations | Alert definitions and runbooks | —
NFR-16 | NFR | 6.3 Observability | Configurable data retention and purge policies (CBB & PDPL). | Not covered | — | Yes | — | Data retention & purge policies (CBB & PDPL) | —
NFR-17 | NFR | 6.4 Architecture & deployment | Containerised on Bede EKS; IaC (Terraform/Helm) for instant deployment to recovery regions. | Not covered | — | No | Infrastructure | Containers on Bede EKS; IaC | —
NFR-18 | NFR | 6.4 Architecture & deployment | Environment parity across dev, UAT and production. | Not covered | — | No | Infrastructure | Environment parity | —
NFR-19 | NFR | 6.4 Architecture & deployment | Built on Apache Fineract or similar open-source platform; upstream version pinned, documented upgrade path, no fork off upstream. | Partly covered | Platform: LMS built on Apache Fineract | Yes | — | Pinned upstream version, upgrade path, no fork (confirm) | —
NFR-20 | NFR | 6.4 Architecture & deployment | Zero-downtime deployments by default; any interruption justified and approved in advance. | Not covered | — | Partly | Deployment pipeline | Zero-downtime deployments | —
NFR-21 | NFR | 6.4 Architecture & deployment | Every deployment supports straightforward, tested rollback. | Not covered | — | Partly | Deployment pipeline | Tested rollback per deployment | —
D-01 | Delivery | 7.1 Discovery | Foo team/expert on site for specification workshops. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-02 | Delivery | 7.1 Discovery | Deliverables: BRD, functional spec, solution architecture, integration specs, data model, signed-off backlog with acceptance criteria. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-03 | Delivery | 7.2 Environments | Bede provisions and manages all AWS environments. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-04 | Delivery | 7.2 Environments | Foo deployment access to development environment only. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-05 | Delivery | 7.2 Environments | Bede deploys UAT/prod using Foo-supplied tested packages & step-by-step guides. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-06 | Delivery | 7.2 Environments | Foo gets PII-masked logs only (NFR-08). | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-07 | Delivery | 7.3 Testing | DoD and acceptance criteria agreed per feature before build. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-08 | Delivery | 7.3 Testing | Foo delivers unit, integration and SIT with evidence; UAT test cases and anonymised test data. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-09 | Delivery | 7.3 Testing | Bede UAT with written sign-off; no Sev1/Sev2 open at go-live. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-10 | Delivery | 7.3 Testing | Performance, pen-test and DR tests are acceptance gates. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-11 | Delivery | 7.4 Documentation | Admin guide, ops runbooks, API docs, deployment & rollback guides, architecture & data model docs. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
D-12 | Delivery | 7.4 Training | Training for ops, finance, risk, compliance, IT; recordings retained by Bede. | Non-product feature | — | No | Project delivery | Delivery obligation – covered in the proposal / SOW and project plan | —
M-01 | Migration | 8 Migration | Migrate all existing customers, contracts, schedules, repayment history, balances and documents. | Not covered | — | Partly | Migration scripts / ETL | Migration of customers, contracts, schedules, history, balances, documents (roadmap #36) | #36
M-02 | Migration | 8 Migration | Field-level data mapping document agreed before first simulation. | Not covered | — | No | Migration deliverable | Field-level mapping document (roadmap #36) | #36
M-03 | Migration | 8 Migration | Reconciliation to the fils on all balances & schedules; report + sign-off as go-live gate. | Not covered | — | Partly | Migration tooling | Reconciliation to the fils; sign-off (roadmap #36) | #36
M-04 | Migration | 8 Migration | Historical repayment history and original contract terms preserved and visible. | Partly covered | Murabaha Profit FRD §8.9 (Contractual Profit captured for existing Murabaha at go-live) | Yes | — | Original terms and history visible after migration (roadmap #36) | #36
M-05 | Migration | 8 Migration | Multiple full simulation cycles using a new app build connected to new LMS, without interrupting existing app. | Not covered | — | No | Migration / app | Full simulation cycles with new app build (roadmap #36) | #36
M-06 | Migration | 8 Migration | Production cut-over downtime ≤ [2 hours]. | Not covered | — | No | Migration plan | Cut-over downtime ≤ 2 hours (roadmap #36) | #36
M-07 | Migration | 8 Migration | Documented & rehearsed rollback plan for cut-over. | Not covered | — | No | Migration plan | Rehearsed rollback plan (roadmap #36) | #36
M-08 | Migration | 8 Migration | Data freeze window, communication plan, post-migration validation checklist. | Not covered | — | No | Migration plan | Data freeze, communication plan, validation checklist (roadmap #36) | #36
S-01 | Support | 9 Hypercare | Hypercare 3–6 months post go-live with on-ground presence and daily review calls. | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
S-02 | Support | 9 Warranty | Warranty 5 years post go-live; all defects corrected at no cost. | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
S-03 | Support | 9 Support | 24x7 support by phone/email/portal, escalation to executive level, English & Arabic. | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
S-04 | Support | 9 SLAs | Sev1 15 min response / 2 h resolution; Sev2 30 min / 8 h; Sev3 4 h / 3 days; Sev4 1 day / next release. | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
S-05 | Support | 9 Monthly items | Monthly security & hotfix release with vulnerability/bug report. | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
S-06 | Support | 9 Monthly items | Monthly service review (SLA, incidents, RCA, capacity, changes). | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
S-07 | Support | 9 Monthly items | Service credits / penalties for SLA breaches (§10). | Non-product feature | — | No | Support model | Support obligation – covered in the support & SLA agreement | —
C-01 | Commercial | 10 Commercial terms | IP: Bede owns all custom code, configuration, documentation and data; source in Bede repo or escrow. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-02 | Commercial | 10 Commercial terms | Milestone payments tied to acceptance; 20% retention released 3 months post go-live. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-03 | Commercial | 10 Commercial terms | Service credits 5% of monthly fee per breach, capped 20%/month; repeated breaches = termination. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-04 | Commercial | 10 Commercial terms | Liquidated damages: 8% of contract value per week of delay. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-05 | Commercial | 10 Commercial terms | Change control with impact assessment; rate card agreed at signature. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-06 | Commercial | 10 Commercial terms | Named key personnel; no subcontracting without consent. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-07 | Commercial | 10 Commercial terms | CBB outsourcing obligations: audit rights, CBB access to Foo premises/staff/records, data location, notification of changes. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-08 | Commercial | 10 Commercial terms | Foo business continuity plan maintained and tested. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-09 | Commercial | 10 Commercial terms | Exit: 6 months transition assistance, return of data & code, destruction certificates. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-10 | Commercial | 10 Commercial terms | NDA + DPA aligned to Bahrain PDPL. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-11 | Commercial | 10 Commercial terms | Liability cap, indemnities (incl. IP), PI / cyber insurance at [amount]. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
C-12 | Commercial | 10 Commercial terms | Term: 5 years support & maintenance, annual renewal, pricing review. | Non-product feature | — | No | Contract | Commercial term – covered in the contract | —
G-01 | Governance | 10 Governance | Monthly steering committee. | Non-product feature | — | No | Project governance | Governance obligation – covered in the project plan | —
G-02 | Governance | 10 Governance | Weekly status report & meeting; shared RAID log. | Non-product feature | — | No | Project governance | Governance obligation – covered in the project plan | —
G-03 | Governance | 10 Governance | Single Foo PM as point of accountability. | Non-product feature | — | No | Project governance | Governance obligation – covered in the project plan | —
G-04 | Governance | 10 Governance | All decisions, scope changes, acceptances in writing. | Non-product feature | — | No | Project governance | Governance obligation – covered in the project plan | —

## Initial Roadmap
# | Workstream | Required Task / Capability | Recommendation / Clarification | Parallelization / Dependency | Required in Initial SOW (Annex 1) | Phases | Note | Estimation in MD | Streams | Owner if BEDE Select Mambu | Estimation If Mambu | Status Description
1 | Partner API / Facade | Tamam-facing REST to replace Optasia (availability, eligibility, register, offers, submit, loans, closing-amount, callbacks) | lms-client is the Optasia replacement. HMAC or WSO2 OAuth. Wallet must switch base URL. Rotate leaked HMAC keys; do not put keys in Jira. | No | No | P1 |  | 6 | Stream 1 | Shared | 6 | Tamam–Mambu integration required
2 | Credit Decisioning | Configurable Risk Acceptance Criteria (RAC) / Hard Eligibility Rules | Define and execute hard eligibility rules such as age, income, employment tenure, write-off, DBR/disposable income, nationality, etc. Can leverage GoRules. | Can start in parallel with scoring integration once rule structure is agreed | No | P1 |  | 3 | Stream 2 | FOO | 3
3 | Credit Decisioning | Borrower Eligibility Check & Decisioning API | Better than “API to check on RAC.” The API should return ELIGIBLE / NOT_ELIGIBLE, rejection reasons and applicable eligibility results. RAC is one input to this decision. | Depends on RAC design; API contract can start in parallel | No | P1 |  |  | Stream 2 | FOO
4 | Credit Decisioning | Credit Scoring Input Attributes & Data Mapping | Existing priority. Define required attributes, source mapping, derived fields and external enrichment required by each scoring model. | Can start immediately in parallel | No | P1 |  |  | Stream 2 | FOO
5 | Credit Decisioning | LMS–Credit Scoring Platform Integration | Existing priority. Covers triggering scoring, request/response mapping, persistence and handling of score/decision/model/execution details. | Can start in parallel with #1 and #3; final testing depends on model/input readiness | No | P1 |  | 2 | Stream L1 | Shared | 1 | FOO Credit Scoring–Mambu integration required
6 | Credit Decisioning / Offers | Risk-Band-Based Product Eligibility & Offer Determination | Determine eligible products, maximum amount, eligible tenure and potentially pricing based on score/risk band. | Depends on scoring outputs/risk bands, but design can start in parallel | No | P1 |  | 5 | Stream L1 | Shared | 1 | FOO decisioning with Mambu product data
7 | Credit Decisioning | Persist decisioning snapshot for audit and care portal | Immutable JSON of RAC/score/offer inputs per eligibility run. Needed for rejection history. | No | No | P1 |  | 1.5 | Stream L1 | Shared | 1 | FOO decisioning results integrated with Mambu
8 | Customer / KYC | Borrower KYC capture, update and deactivate (EN/AR) | Fineract client is system of record. LMS maps Optasia borrower APIs onto create/update/close client plus datatables. | No | No | P1 |  | 3 | Stream 2 | Shared | 1 | Integration Effort - Mambu becomes the customer system of record, while FOO still needs to connect the Tamam customer journey to Mambu
9 | Customer / KYC | Enforce one active loan per customer | Not a Fineract product switch. LMS pre-check plus ledger guard. Confirm whether Closed/Cancelled frees the slot. | No | No | P1 |  | 1 | Stream 2 | Mambu | 1
10 | Islamic Financing-Core | Murabaha Profit Configuration, Fixed Profit Schedule Allocation & Rescheduling Controls | Existing priority Your existing Murabaha scope can cover the Islamic-financing requirements needed by the target solution. | Independent workstream – can run fully in parallel | Yes | P1 |  | 6 | Stream L2 | Mambu | 6
|  | Murabaha Lifecycle & Sale Execution Controls, Maker-Checker, Audit & Evidence Management |  |  | Yes | P1 |  | 4 | Stream L2 |  | 4
|  | Ibra' & Early Settlement |  |  | Yes | P1 |  | 2 | Stream L2 |  | 2
|  | Takaful / Insurance Classification & Treatment |  |  | Yes | P1 |  | 3 | Stream L2 |  | 3
|  | Late Payment & Charity Accounting , Management |  |  | Yes | P1 |  | 7 | Stream L2 |  | 7
|  | Murabaha Accounting, GL, Profit Suspension & Odoo Integration |  |  | Yes | P1 |  | 18 | Stream L2 |  | 18
|  | CBB Consumer Disclosure |  |  | Yes | P1 |  | 3 | Stream L2 |  | 3
11 | Islamic Financing | Murabaha Documents & Template Management | Existing priority Your existing Murabaha scope can cover the Islamic-financing requirements needed by the target solution. | Independent workstream – can run fully in parallel | Yes | P1 |  | 6 | Stream L1 | Mambu | 6
|  | Multi-Currency Purchase & FX |  |  | Yes | P1 |  | 7 | Stream L1 |  | 7
|  | IFRS 9 / CBB ECL Integration |  |  | Yes | P1 |  | 7 | Stream L1 |  | 7
|  | Wakala Workflow |  |  | Yes | P1 |  | 7 | Stream L1 |  | 7
|  | Tawarruq & Commodity Transaction Integration |  |  | Yes | P1 |  | 12 | Stream L1 |  | 12
|  | Wa'd & Hamish Jiddiyyah |  |  | Yes | P1 |  | 5 | Stream L1 |  | 5
|  | Grace / Moratorium / Balloon / Step-up Structures |  |  | Yes | P1 |  | 2 | Stream L1 |  | 2
12 | Early Settlement | Early Settlement Event / Trigger Support | Define the settlement-specific event used for charges, interest treatment, advices, accounting, etc. | Can start in parallel with other early-settlement items | Yes | P2 |  | 2 | Stream L1 | Mambu | 2
13 | Early Settlement | Early Settlement Fee / Charge Support | Allows a charge specifically triggered by early settlement. | Partially parallel; depends on settlement event/trigger design | Yes | P2 |  | 3 | Stream L1 | Mambu | 3
14 | Early Settlement | Early Settlement Fee Waiver | Support selective/all applicable fee waiver during settlement if required. | Partially parallel; depends on fee handling design | No | P2 |  | 2 | Stream L1 | Mambu | 2
15 | Early Settlement | Early Settlement Interest / Profit Adjustment | Define discount/recalculation of remaining interest/profit when settling early. | Can be developed in parallel with fee work but integrated together | Partially | P2 | SOW requires accrued profit up to settlement date as part of the calculation, but does not define Optasia-style profit discount/waiver behavior. | 2 | Stream L1 | Mambu | 2
16 | Notifications | Loan Notifications & Reminder Orchestration | Covers event-driven advices plus scheduled EMI reminders, delinquency reminders and recurring collection notifications. Advices framework already covers much of the event-driven portion. | Can run in parallel; event reminders depend on source events being available | No | P1 |  | 4 | Stream 1 | Shared | 3 | Mambu events integrated with FOO customer channels
17 | Origination / Workflow | LMS Loan Origination & Status Workflow Enhancements | Specify the missing Optasia lifecycle/status/callback behavior under this workstream. | Can start in parallel, but exact estimate depends on missing lifecycle gaps | Partially | P1 | SOW requires lifecycle status tracking and backend offer creation/customer acceptance, but not the exact Optasia workflow/status/callback model. | 3 | Stream L2 | Shared | 1 | Mambu owns loan lifecycle; FOO must map Tamam journeys/statuses/callbacks to Mambu.
18 | Origination / Offers | Loan Offer Caching & Refresh | Covers caching offer results and forced recalculation/refresh where required. | Can run in parallel with offer decisioning; depends on final offer API contract | No | P2 |  | 3.5 | Stream L2 | FOO | 1 | Check if currently available and no more effort
19 | Origination | Application Expiry & Automatic Cancellation | 72 hours can be the configured value for the implementation. | Independent enough to run in parallel | No | P2 |  | 2 | Stream L2 | Mambu | 2
20 | Pricing / Promotions | Promo Code & Promotional Discount Support | Clarify whether promo codes affect administration fees, pricing, profit/interest, or another charge. | Can run in parallel; depends on whether promo impacts fees, rate, or both | No | P2 |  | 2 | Stream L2 | Shared | 1 | Tamam promotion flow with Mambu pricing/fees
21 | Payments / Integration | External Repayment & Bank Reconciliation Integration | Integrate LMS with payment gateways and banking channels for inbound repayment processing and reconciliation of LMS customer outstanding balances against inward and outward bank cash movements. | Can start in parallel once external provider contracts/APIs are available | Yes | P1 | The SOW explicitly says Payment Channel Integration must integrate with payment gateways and banking channels for “inbound repayment processing and reconciliation.” | 10 | Stream X | Shared | 5 | External repayment integration with Mambu
22 | Accounting | Accounting / ERP Integration |  | Can run in parallel; reuse existing accounting integration where possible | Yes | P2 |  | 5 | Stream 1 | Mambu | 5
23 | Customer Service | CRM / Ticketing Integration | Ticketing should normally be owned by CRM/helpdesk rather than rebuilt inside Fineract. | Independent workstream – can run in parallel | Partially | P2 | CRM integration = Yes; ticketing/helpdesk specifically = not stated. SOW requires bidirectional CRM synchronization/workflow coordination. | 2 | Stream 1 | Shared | 2 | Confirm CRM/ticketing integration ownership | before STream X
24 | Customer Data | Borrower Data Refresh / Re-registration | Fineract client update may cover most of it; dedicated refresh orchestration needs validation. | Can run in parallel after refresh behavior is confirmed | No | P2 |  | 2 | Stream L2 | Mambu | 2
25 | Product / Pricing | Regulatory APR Calculation | Refer to APR Sheet | Automatically calculate APR for regulatory disclosure. This was identified in our Optasia analysis as well, but is missing from your replacement-task summary. | Yes | P2 |  | 0 | Stream L1 | Mambu | 2
26 | Delinquency / Accounting | 90+ DPD Profit Accrual Suspension | Automatically identify agreements exceeding 90 DPD and stop profit accrual on those accounts. This is more than normal delinquency classification. |  | Yes | P2 | Validate whether Fineract's NPA/delinquency configuration stops accrual automatically once the configured DPD threshold is reached | 2.5 | Stream L1 | Mambu | 2.5
27 | Repayment (wallet/Cheque/Card) | EMI schedule, oldest-unpaid-first allocation, and partial repayment held until a full EMI | Fineract schedule and allocation are configurable. Tamam internal wallet vs advance payment must be confirmed before building a new wallet. | No | No | P2 |  | 2.5 | Stream L2 | Mambu | 2.5
28 | Write-Off | Partial & Full Loan Write-Off | Full write-off exists in Fineract/FOO, but SOW1 specifically asks for partial and full write-off, including accounting entries and audit. The key item to validate is partial write-off. |  | Need Verification | P2 |  | 2 | Stream L2 | Mambu | 2
29 | Business & System Configuration Management |  |  |  | Yes | P1 | 2.5 | 5 | Stream P | Mambu | 5
30 | Real-Time Management & Financial Dashboards | Profit Income & Yield Analysis/Receivable & Deferred Profit Movement Dashboard/Enhanced Aging Analysis – Outstanding & Deferred Profit | Enhance the existing LMS Dashboard to provide portfolio-level profit income and yield analysis... as required by SOW1. This should extend the existing dashboard rather than create a new dashboard capability. Refer to Dashboard Requirements Sheet |  | Yes | P2 | Can be developed in parallel with other dashboard enhancements; depends on availability and accuracy of profit/income data | 2 | Stream R | TBD | 2
31 | Operational, Financial & Regulatory Reporting | AAOIFI / FAS Reporting | AAOIFI-compliant accounting/reporting; provisioning and future ECL support |  | Yes | P2 |  | N/A | Stream R | TBD | N/A
32 | Operational, Financial & Regulatory Reporting | Deferred / Unearned Profit Movement Report | Profit charged, closed-account reversals, new disbursements |  | Yes | P2 |  | N/A | Stream R | TBD | N/A
33 | Operational, Financial & Regulatory Reporting | Receivable Balance Movement Report | New disbursements, repayments, closed-account reversals, write-offs |  | Yes | P2 |  | N/A | Stream R | TBD | N/A
34 | Operational, Financial & Regulatory Reporting | Regulatory Reporting – CBB | Reports aligned with Central Bank of Bahrain requirements |  | Yes | P2 |  | N/A | Stream R | TBD | N/A
35 | Operational, Financial & Regulatory Reporting | Aging & Delinquency Reporting | DPD buckets, >90 DPD, legal fees/penalties, 3–36 month aging, repayment delays, maximum historical delinquency |  | Yes | P2 |  | N/A | Stream R | TBD | N/A
36 | Data Migration |  |  |  | No | P1 |  | 10 | Stream M | Mambu | 10
| TOTAL | Sum of Estimation in MD (1 developer). Vendor wait and BEDE UAT calendar are outside these numbers. | [5 empty] | 177 |  |  | 160
Check Credit Scoring Security
2.25